## Sheet1
Equity – Ebanking Project
S/N | Tasks | Responsibility | Hours | Start Date | Start Time | End Time | End Date | Duration | Status | OS
1 | Accessing the server | USG |  | 2025-02-11 |  |  | 2025-02-11
2 | Request for backup dump and forms(18-Feb-25 post dump) | Equity |  | 2025-03-03
3 | Movement of server to Union systems office for installation | Equity |  | 2025-03-03
4 | Data restore | Equity |  | 2025-03-04 |  |  | 2025-03-04
5 | VM installation | USG |  | 2025-03-04 |  |  | 2025-03-04
6 | Api server | USG |  | 2025-03-04 |  |  | 2025-03-04 |  |  | Oracle linux 9 | java 21
7 | Agency server | USG |  | 2025-03-04 |  |  | 2025-03-04 |  |  |  | tomcat 10
8 | Internet Banking and mobile apps | USG |  | 2025-03-04 |  |  | 2025-03-04
9 | Testing | USG |  | 2025-03-04 |  |  | 2025-03-13
10 | Movement of server from Union Systems to Equity | USG |  | 2025-03-14 |  |  | 2025-03-14
11 | Request for IPs | Equity/USG |  | 2025-03-14 |  |  | 2025-03-14
12 | Testing | Equity I.t / USG |  | 2025-03-17 |  |  | 2025-03-28
13 | Uat | Equity/USG |  | 2025-04-01 |  |  | 2025-04-30
14 | Go Live | Equity |  | 2025-05-01 |  |  | 2025-05-01