## 7-June-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 80% | 2019-06-14 | Finlizing on design
|  | Transfer Enquiry | M | 2019-05-20 | USG | 80% | 2019-06-14 | Finlizing on design
|  | Alert Enqiry | M | 2019-05-20 | USG | 80% | 2019-06-14 | Finlizing on design
|  | Import LC Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 | USG | 10% | 2019-06-14 | WIP
|  | Used Cheque number Enquiry | M | 2019-06-07 | USG | 100% | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully

## 14-June-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 | USG | 100% | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 | USG | 100% | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 90% | 2019-06-19 | Done and implemented. GN Liberia test successful , UTB to be tested.
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 70% | 2019-06-21 | WIP, Completed within target date

## 21-June-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 | USG | 100% | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 | USG | 100% | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 | USG | 85% | 2019-07-30 | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 90% | 2019-06-21 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Completed, tested and implemented succesfully

## 28-June-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 |  |  |  | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 |  |  |  | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 |  |  |  | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 |  |  |  | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 |  |  |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 |  |  |  | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 90% | 2019-06-21 |  |  |  | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 |  |  |  | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 |  |  |  | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 |  |  |  | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 |  |  |  | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 70% | 2019-07-26 |  |  |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 0% | 2019-07-26 |  |  |  | Create a screen or app outside x.100 to generate license file.

## 05-July-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 80% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 80% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | (Add report module) modificatiion | M | 2019-07-02 | USG | 50% | 2019-07-12 | N | N |  | WIP
|  | (Update report module) modification | M | 2019-07-02 |  | 100% | 2019-07-05 | N | N | 2019-07-03 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed

## 12-July-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | (Add report module) modificatiion | M | 2019-07-02 | USG | 60% | 2019-07-12 | N | N |  | WIP
|  | (Update report module) modification | M | 2019-07-02 |  | 100% | 2019-07-05 | N | N | 2019-07-03 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 85% | 2019-07-17 | Y | N |  | WIP
14 | Form Standardization | Design & Documentation | H | 2019-07-10 | USG | 85% | 2019-07-17 | Y | N |  | WIP

## 19-July-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 10% | 2019-08-02 | N | N |  | WIP
|  | Account/Tax | H | 2019-07-18 |  | 10% | 2019-08-02 | N | N |  | WIP

## 26-July-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 80% | 2019-08-02 | N | N |  | WIP
|  | Account/Tax | H | 2019-07-18 |  | 80% | 2019-08-02 | N | N |  | WIP

## 02-August-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 90% | 2019-08-02 | N | N |  | completed
|  | Account/Tax | H | 2019-07-18 |  | 90% | 2019-08-02 | N | N |  | completed

## 09-August-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Alert Service Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 90% | 2019-08-02 | N | N |  | completed
|  | Account/Tax | H | 2019-07-18 |  | 90% | 2019-08-02 | N | N |  | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 90% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 0% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)

## 16-August-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 90% | 2019-07-26 | N | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 90% | 2019-07-26 | N | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 90% | 2019-08-02 | N | N |  | completed
|  | Account/Tax | H | 2019-07-18 |  | 90% | 2019-08-02 | N | N |  | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 90% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 0% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)

## 23-August-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N |  | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N |  | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 90% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 0% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 85% | 2019-08-30 | N | N |  | WIP, Completed within target date

## 30-August-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 90% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 0% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 100% | 2019-08-30 | Y | N | 2019-08-27 | completed

## 06-September-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 100% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 0% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 100% | 2019-08-30 | Y | N | 2019-08-27 | completed

## 13-September-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 100% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 90% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 100% | 2019-08-30 | Y | N | 2019-08-27 | completed

## 20-September-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 95% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 95% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 100% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 90% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 100% | 2019-08-30 | Y | N | 2019-08-27 | completed

## 27-September-2019 (hidden)
Sr. No | Main Task | Sub-Tasks | Priority (H/M/L) | Start Date | Client | % Completed | Target Date | Tested (Y/N) | Implemeted (Y/N) | Completion Date | Current Update
1 | Enqury | Verified User Transaction Enquiry | M | 2019-05-20 | USG | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Transfer Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Alert Enqiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import LC Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Import Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Export Bill for Collection Enquiry | M | 2019-05-20 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Cheque Book Listing Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
|  | Used Cheque number Enquiry | M | 2019-06-07 |  | 100% | 2019-06-14 | Y | N | 2019-06-14 | Completed
2 | BestPoint Upgrade | ATM Request Approval | M | 2019-06-03 | Bestpoint | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Old Card Replacement Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Request | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Approval | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
|  | ATM Regeneration Issuance | M | 2019-06-03 |  | 100% | 2019-06-08 | Y | Y | 2019-06-08 | Completed, tested and implemented succesfully
3 | Additional Statement | Statement Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment | M | 2019-02-05 |  | 95% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Amendment Approval | M | 2019-02-05 |  | 95% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Deactivation Approval | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
|  | Statement Request Enquiry | M | 2019-02-05 |  | 90% | 2019-07-30 | N | N |  | Done, to be tested and finalize on design
4 | Alert Services | Alert Service Request | M | 2019-02-05 | USG | 100% | 2019-07-30 | Y | N | 2019-08-16 | completed
|  | Alert Service Request Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-17 | completed
|  | Alert Service Amendment | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-18 | completed
|  | Alert Service Amendment Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-19 | completed
|  | Alert Service Deactivation | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-20 | completed
|  | Alert Service Deactivation Approval | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-21 | completed
|  | Alert Service Enquiry | M | 2019-02-05 |  | 100% | 2019-07-30 | Y | N | 2019-08-22 | completed
5 | Management Report Setup | Send Managers Report Form | H | 2019-06-13 | UTB/GN Liberia | 100% | 2019-06-19 | Y | Y | 2019-06-19 | Completed, tested and implemented succesfully
6 | Migration/Testing | Setups/Operation | M | 2019-06-11 | Golden Pride | 100% | 2019-06-21 | Y | N | 2019-07-05 | WIP, Completed within target date
7 | ATM Reports (Bestpoint Upgrade) | ATM Old Card Replacement Report | M | 2019-06-17 | Bestpoint | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
|  | ATM Regeneration Report | M | 2019-06-17 |  | 100% | 2019-06-17 | Y | Y | 2019-06-17 | Completed, tested and implemented succesfully
8 | Cash Operation | Imprest Withdrawal | M | 2019-06-20 | UTB | 100% | 2019-06-20 | Y | Y | 2019-06-20 | Completed, tested and implemented succesfully
9 | User Login/Logout (Define Time ) | Define User Login/Logout Time by the Bank | M | 2019-06-17 | Atwima/USG | 100% | 2019-06-21 | Y | Y | 2019-06-21 | System check the time users are to login and logout by defining user time and validating with database time(Completed, tested and implemented succesfully)
10 | x.100 Software License | Software License Expiry | H | 2019-06-26 | USG | 100% | 2019-07-26 | Y | N |  | system checks for expiry, pirated and also promt users of grace period before expiry.
|  | Technology to generate License File | H | 2019-06-26 |  | 100% | 2019-07-26 | Y | N |  | Java application has been developed to generate License Key, Testing is ungoing
11 | Add Report Module | Add Managers Report | M | 2019-07-02 | USG | 100% | 2019-07-12 | N | N | 2019-07-19 | completed
12 | Migration | Bestpoint Migration | H | 2019-07-04 | Bestpoint | 100% | 2019-07-05 | Y | N | 2019-07-05 | completed
13 | Migration & Testing(Operation) | GN Migration | H | 2019-07-09 | GN | 100% | 2019-07-17 | Y | N | 2019-07-19 | completed
14 | Form Standardization | Form Standard Design & Documentation | H | 2019-07-10 | USG | 100% | 2019-07-17 | Y | Y | 2019-07-19 | completed
15 | Fees Setup | Fees Definition | H | 2019-07-18 | USG | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
|  | Account/Tax | H | 2019-07-18 |  | 100% | 2019-08-02 | Y | N | 2019-07-31 | completed
16 | X.100 Menu Structure | Define Menu Structure in Excel | M | 2019-08-02 | USG | 100% | 2019-08-09 | Y | N | 2019-08-07 | completed
|  | Implement Menu Structure | M | 2019-08-09 |  | 90% | 2019-08-30 | Y | N |  | Awaiting confirmation of the excel menu structure (Excel Sample)
17 | Add Form Module | Add Form | M | 2019-08-21 | USG | 100% | 2019-08-30 | Y | N | 2019-08-27 | completed
18 | X.100 R18 Upgrade | Bestpoint Migration | M | 2019-09-21 | USG | 100% | 2019-09-23 | Y | N | 2019-09-23 | completed
|  | Bestpoint Go-Live Support | M |  |  | 50% | 2019-09-24 | Y | N | 2019-10-31 | WIP

## Atwima
AKRB Upgrade
Department | Data List | Resource | Comments
Finance | Chart of Account | PRINCE M
| Trial Balance | PRINCE M
| Balance Sheet | PRINCE M
| Profit n Loss (PNL) | PRINCE M
| Fixed Asset | PRINCE M
Overall Total (%)