## download (20)
[5 empty] | COLOUR | MEANING
0 - 6 DAYS
7 - 15 DAYS
16 DAYS AND ABOVE
SEVERITY 1
Assigned Issues
Id | Date_Logged | Ticket_Id | Incident_Summary | Incident_Details | Person_Affected | Comment | Technical Person | Logged By | Relations Manager | Affected_Area | Severity | Client_Name | Days_Pending | Status | Resolution_Details | Resolved_Date | Root_Cause
1 | 2022-05-12 13:22 | IN00006464 | MANAGERS /EXECUTIVE APPROVAL & NOTIFICATION SYSTEM | Approvals for Managers and EXCO should have remote (mobile) access capability. In addiotion thefre should be a notification prompting attention required | Management | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-12 13:23:52 | Nii Ayi Welbeck | Alhaji Lewally | Nii Ayi Welbeck | Cash Operation / Teller | 3 | Rokel Commercial Bank | 0 days
2 | 2022-05-12 13:07 | IN00006463 | DATA REQUEST | Hi Commandcenter, Kindly provide me a report with the following fields as at 31st December 2021: BALANCE_DATE CUSTOMER_ACCOUNT_NUMBER CUSTOMER_NAME ARM ARM_CODE BUSINESS UNIT CURRENCY COT AMOUNT FEES AND COMMISSION INTEREST AMOUNT BARNCH | ANSUMANA KEITA | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-12 13:18:31 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Online Reports | 3 | SIERRA LEONE COMMERCIAL BANK | 0 days
3 | 2022-05-11 16:00 | IN00006462 | ERROR IN NRA PAYMENT | Hello team, We have just notice from one of our cashier ALBERTINA ADAMA KANU with float account number 003003037561113193 that she was trying to processed NRA transaction with PRN number 00000000046785 SLL 95,299,550 but received an error message stated PAYMENT ALREADY MADE FOR THE GIVEN PRN NUMBER. His float account was not hit by the said amount and unable to print receipt for the customer. Upon investigation a staff from NRA and the customer in question had confirmed that ,the transaction had already hit their system but did not hit our core banking. pls help us on this issue. regards. | Ibrahim Bangura | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-12 09:32:02 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 1 days
4 | 2022-05-11 12:05 | IN00006461 | USSD TRANSACTION ISSUE | Upon two Account to Wallet transaction, the mobile money wallet of the customer was credited twice but contra account at Best Point was debited once. Account number sample : 0008472203100 Transaction details; 02BO392894F6394 - 2022-05-10 21:21:31 02LH39376A79290 - 2022-05-10 21:24:20 | Daniel | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-05-11 12:08:26 | Nii Ayi Welbeck | DANIEL KORANTENG | Nii Ayi Welbeck | Not Working | 3 | Best Point | 1 days
5 | 2022-05-10 14:55 | IN00006460 | DIFFERENCE IN BRANCH LIMIT REPORT | kindly find attached excel depicting differences noted in the branch cash as at 29/4/22. The physical cash figure, GL balance and Head Teller Till (vault balance) are the same whilst the branch cash control limit report used by Compliance to confirm cash balance /figure is different for Wilkinson Road and Mobimbi branch. We need to understand the root cause of such discrepancy and the issue need to be resolved. Previously it was just Wilkinson Road that had a difference of Le 5,665,000.00 but Mobimbi branch is also showing a difference of Le 28,490,000.00 as at close of business on 29/4/22. | Hannah T.Ngobeh | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-10 14:57:36 ********COMMENT 2 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-10 14:57:37 ********COMMENT 3 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-10 14:57:39 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 2 days
6 | 2022-05-10 08:37 | IN00006458 | ISSUE WITH ACCOUNT CLASSIFICATION / PROVISION (SUMMARY) REPORT | We have noticed that figures of ACCOUNT CLASSIFICATION / PROVISION (SUMMARY) REPORT is far higher than the provision amount that we have done in the system. Kind investigate and rectify. | Khalid | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-10 09:09:42 | Nii Ayi Welbeck | DANIEL BLANKSON | Nii Ayi Welbeck | Loan / Credit | 3 | EQUITY SAVINGS AND LOANS | 2 days
7 | 2022-05-09 14:33 | IN00006456 | DUPLICATION OF TRANSACTIONS | Matured FDs were credited twice to customers and also USSD transactions are showing double in customers accounts. Kindly help us fix the above issue ASAP. Thank you. | Christian Ashun | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-09 14:35:15 ********COMMENT 2 ***** Reply From Nii Ayi : Alex, kindly update ticket. i learnt something went wrong during EOD yesterday and you were supporting [Date Posted] :2022-05-09 15:22:49 | ALEX AGYEI | Christain Ashun | Nii Ayi Welbeck | Operations | 3 | Best Point | 3 days
8 | 2022-05-09 13:18 | IN00006454 | CASH DIFFERENCE- KISSY BRANCH MARCH 2022 | Please find attached cash certificate in respect of the above report showing difference between the branch cash control report (SLL 4,759,211,600) used by Compliance to verify the physical cash counted ( SLL 4,764,866,600.00) at Kissy Branch on the 31/3/22 throwing a difference of SLL 5,655,000.00 Kindly explain the root cause and ensure error is corrected. This issue is very much serious and it is gradually reaching at an alarming age. Please take it very serious. | Ishmail Sillah | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-09 13:20:54 ********COMMENT 2 ***** Reply From Hamza Alieu : Prince kindly take it from here as discussed. Thanks [Date Posted] :2022-05-09 13:24:28 ********COMMENT 3 ***** Reply From Hamza Alieu : Prince kindly take it from here as discussed. Thanks [Date Posted] :2022-05-09 13:36:59 | Prince Manu | Mohamed L Jalloh | Nii Ayi Welbeck | Cash Operation / Teller | 3 | SIERRA LEONE COMMERCIAL BANK | 3 days
9 | 2022-05-09 12:00 | IN00006452 | USSD TRANSACTION DOUBLE ENTRIES | The USSD credits customers double the amount they transact. Sample accounts : 1600687146100 , 1600702146100 ,1700326701100,0600541310100 Kindly help resolve asap | DANIEL | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-09 12:11:10 ********COMMENT 2 ***** Reply From Stephen : As discussed. Kindly provide the RCA [Date Posted] :2022-05-09 13:21:06 | Jude Kuwornu | DANIEL KORANTENG | Nii Ayi Welbeck | Not Working | 3 | Best Point | 3 days
10 | 2022-05-06 20:31 | IN00006451 | ST MARYS ATM VARIANCE | On the 3rd may,2022 the ATM was replenished with Le80,000,000. However a variance was discovered between the physical cash retrieved from the ATM and the GL.The GL balance as at the replenished date was Le3,490,000 and the physical cash retrieved from the ATM was Le2,790,000. The GL was credited on the 4th may,2022 with the cash retrieved from the ATM. Kindly provide help to resolve the variance of Le700,000 | Clifford Turner | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help [Date Posted] :2022-05-07 11:06:49 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 6 days
11 | 2022-03-30 16:43 | IN00006351 | ISSUE WITH LOAN ORIGINATION | We have realized that when originating a loan and get the processing fee field, the system raise an error. | Khalid | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-03-30 16:45:54 ********COMMENT 2 ***** Reply From Nii Ayi : For your attention [Date Posted] :2022-04-06 16:33:04 ********COMMENT 3 ***** Reply From Joseph : Kindly chekout with Caleb for their forms [Date Posted] :2022-04-20 08:35:32 | ALEX AGYEI | DANIEL BLANKSON | Nii Ayi Welbeck | Loan / Credit | 3 | EQUITY SAVINGS AND LOANS | 43 days
12 | 2022-02-25 09:33 | IN00006239 | AMENDMENT OF CUSTOMERâ€™S DETAILS FOR ACCOUNTS OPENED AT ANOTHER BRANCH BEFORE THE CARD IS REQUESTED | Amendment of customerâ€™s details for accounts opened at another branch before the card is requested â€“ The CSOs are unable to request cards for an old account â€œerror message; First Name, DOB or Sex mandatoryâ€ unless they amend the details and approved before they can request successfully. So, accounts opened at another branch must be amended by the same branch. | Victor Kanu | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-02-25 09:40:28 ********COMMENT 2 ***** Reply From Nii Ayi : Mohammed, Kindly follow up with Richard on this amendments [Date Posted] :2022-02-28 11:38:53 | Mohamed Bah | Union Issues Management Team | Nii Ayi Welbeck | Customer Service | 3 | Rokel Commercial Bank | 76 days
13 | 2021-12-17 15:15 | IN00005976 | ISSUE WITH BULK SMS | We have realized that whenever we send bulk SMS, one customer having one or more additional account gets the duplicate SMS in-respect of number of accounts the customer has. | Dan | ********COMMENT 1 ***** Reply From Helpdesk : Kindly check the issue. Thanks [Date Posted] :2021-12-17 15:31:50 ********COMMENT 2 ***** Reply From Stephen : fya [Date Posted] :2022-01-06 13:02:30 | Richard Tawiah-Baddoo | DANIEL BLANKSON | Nii Ayi Welbeck | Others | 3 | EQUITY SAVINGS AND LOANS | 146 days
14 | 2021-09-23 10:39 | IN00005729 | THE ACCOUNT STATISTICS REPORT FOR CLIENTS DOES NOT SHOW COT AND INTEREST CHARGED TO THE CLIENTS FOR FEBRUARY 2021. | Where as clients were debited for COT and Interest, these charges do not appear in the account statistics report for the month of February 2021 | Kelvin Terry | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2021-09-23 11:08:13 ********COMMENT 2 ***** Reply From Naa : FYA [Date Posted] :2021-10-14 08:26:29 | Richard Tawiah-Baddoo | BAIMBA BOCKARIE | Naa Ashianor | Others | 3 | Union Trust Bank | 231 days
Work In Progress
Id | Date_Logged | Ticket_Id | Incident_Summary | Incident_Details | Person_Affected | Comment | Technical Person | Logged By | Relations Manager | Affected_Area | Severity | Client_Name | Days_Pending | Status | Resolution_Details | Resolved_Date | Root_Cause
1 | 2022-05-09 18:25 | IN00006457 | OVERDRAFT DIFFERENCE IN THE BALANCE SHEET AS AT 29-APR-2022 | we observe a difference of 25,669,472.00 between the Advances figures in the balance sheet and that of the overdraft report as at 29-APR-2022. It reads 238,869,984,811.85 and 238,844,315,339.85 respectively.Kindly take action and revert. Attach are images for ease of reference. | SHEKA THORONKA | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-05-10 09:10:30 ********COMMENT 2 ***** Reply From Stephen : No difference between statement. Please let them spool without choosing currency or print all currencies and add up. [Date Posted] :2022-05-10 09:51:38 | Nii Ayi Welbeck | Jonah Onesimus | Nii Ayi Welbeck | Loan / Credit | 3 | Rokel Commercial Bank | 3 days
2 | 2022-05-06 12:51 | IN00006449 | NEW REPORT FOR BUSINESS DEVELOPMENT OFFICERS | â€¢ A summary report for each RO where one can access a summary of total deposits and loans in their name â€¢ A detailed report where a BDO can see details of all loans and deposit accounts in their name and number of accounts assigned to them. | David Sackeyfio | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help [Date Posted] :2022-05-07 11:07:32 ********COMMENT 2 ***** Reply From Nii Ayi : PLEASE PROVIDE A TEMPLATE FOR THIS REPORT, INCLUDING THE PARAMETERS TO USE. THANKS [Date Posted] :2022-05-09 15:05:39 ********COMMENT 3 ***** Reply From David : TEMPLATE HAS BEEN SENT TO YOUR MAILBOX.THANKS [Date Posted] :2022-05-10 11:31:09 ********COMMENT 4 ***** Reply From David : Please can we get an update on status of work as the Bushiness team need the report ASAP. [Date Posted] :2022-05-11 10:36:19 | Nii Ayi Welbeck | David F. sackeyfio | Nii Ayi Welbeck | Online Reports | 3 | Best Point | 6 days
3 | 2022-05-05 20:55 | IN00006447 | IN BALANCE TILL | Hello all, user name Saidu I. S bangura has an in balance of -177,150,041.34. please help us clear the issue and also help us close Youyi Building Branch. | Saidu I S bangura | ********COMMENT 1 ***** Reply From Hamza Alieu : Resolved [Date Posted] :2022-05-06 08:46:01 ********COMMENT 2 ***** Reply From Hamza Alieu : Alex your action needed here [Date Posted] :2022-05-06 20:06:33 ********COMMENT 3 ***** Reply From Hamza Alieu : Working in progress [Date Posted] :2022-05-06 20:07:23 | ALEX AGYEI | Mr Momoh Konneh | Nii Ayi Welbeck | Back Office | 3 | SIERRA LEONE COMMERCIAL BANK | 7 days
4 | 2022-05-04 19:02 | IN00006445 | TOD WRONG FEE APPLICATION | 100% fee was charged for all TOD created on the 3rd May which caused an imbalance in the system. | Mohammed | ********COMMENT 1 ***** Reply From ALEX : Kindly assist.. [Date Posted] :2022-05-04 19:03:00 | ALEX AGYEI | ALEX AGYEI | Nii Ayi Welbeck | Loan / Credit | 3 | Rokel Commercial Bank | 8 days
5 | 2022-04-29 21:31 | IN00006439 | CASH IN ATM- MAKENI | Team, I hereby write to report a discrepancy of Le 3,500,000 between the ATM physical cash and system cash at 4: 50pm 29th April 2022 . The physical cash in the ATM was LE 3,410,000 whilst the system cash was LE6,910,000. grateful if you could please look into this issue and advice us accordingly as to what we should do when such situation arises. | MARIAMA KALLON | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-30 12:36:25 ********COMMENT 2 ***** Reply From Hamza Alieu : Investigations still ongoing [Date Posted] :2022-05-03 08:40:32 | Nii Ayi Welbeck | Mr Momoh Konneh | Nii Ayi Welbeck | Back Office | 3 | SIERRA LEONE COMMERCIAL BANK | 13 days
6 | 2022-04-29 13:14 | IN00006438 | ISSUE WITH TRIAL BALANCE | The actual placement balance is not in agreement with the balance on the GL. The actual Borrowing balance is not in agreement with the balance on the GL. | Clarence Baysah | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-04-29 13:15:55 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-04-29 13:47:00 ********COMMENT 3 ***** Reply From Stephen : Any initial checks using the account balance enquiry? [Date Posted] :2022-04-29 13:47:49 ********COMMENT 4 ***** Reply From Stephen : . [Date Posted] :2022-04-29 14:28:12 ********COMMENT 5 ***** Reply From Stephen : SIB, any initial checks using the account balance enquiry? [Date Posted] :2022-04-29 14:29:24 ********COMMENT 6 ***** Reply From Stanley : balances on trial balance is correct. jude, please look at your reports [Date Posted] :2022-04-29 19:30:10 ********COMMENT 7 ***** Reply From Stephen : Investigation ongoing. Issue expected to be resolved this week.. [Date Posted] :2022-05-03 11:15:07 ********COMMENT 8 ***** Reply From Stephen : Issue resolved. Kindly check and confirm [Date Posted] :2022-05-09 11:17:25 ********COMMENT 9 ***** Reply From Stephen : SIB has to carry out below entries to correct the difference... BORROWING: Pass a manual posting to reverse reversal transaction posted on 5TH February 2022 with Batch Number 202202051761. Credit 411200000002 CENTRAL BANK OF LIBERIA â€“ USD and Debit 0000477100015 AFRILAND FIRST BANK LIBERIA LIMITED with amount 500,000.00 USD PLACEMENT: Pass a manual posting to reverse reversal transaction posted on 5TH June 2020 with Batch Number 202006052801. Credit 0000166000014 ACCESS BANK LIBERIA LIMITED and Debit 111200000001 CENTRAL BANK OF LIBERIA â€“ LD with amount 164,700,000.00 LRD [Date Posted] :2022-05-11 08:09:06 | Jude Kuwornu | Robert Williams | Stephen Yao Agbeli | Finance | 3 | SIB Bank Liberia | 13 days
7 | 2022-04-25 10:04 | IN00006419 | E-LEVY CHARGES | We kindly request the current USSD API to be updated to include the upcoming E-levy charges. A skype group has been already been created for the purpose. We would be glad if this could be completed by close of business this week | DANIEL | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-25 10:48:44 ********COMMENT 2 ***** Reply From Nii Ayi : API has been modified, waiting for test environment to deploy for testing. [Date Posted] :2022-05-05 15:46:34 | Nii Ayi Welbeck | DANIEL KORANTENG | Nii Ayi Welbeck | Not Working | 3 | Best Point | 17 days
8 | 2022-04-22 14:59 | IN00006413 | DANGOTE PAYMENT | Dear Team we are getting this error message "Transaction rejected by Dangote" when posting Dangote transactions. Please treat with all urgency. | EDWARD B KAMARA | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-22 15:00:51 ********COMMENT 2 ***** Reply From Hamza Alieu : Danny Kindly change status [Date Posted] :2022-04-25 15:56:25 ********COMMENT 3 ***** Reply From Hamza Alieu : . [Date Posted] :2022-04-25 15:57:57 | Daniel Nii Ayi Hammond | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 20 days
9 | 2022-04-22 11:01 | IN00006410 | CUSTOMERS NOT RECEIVING END OF MONTH SMS | Customers are not receiving sms for sms charges for the month when End of Month is run. | Customers | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-04-22 11:28:28 ********COMMENT 2 ***** Reply From Stephen : Setup to be cheched [Date Posted] :2022-04-24 21:34:47 ********COMMENT 3 ***** Reply From Stephen : Sample account required for investigation [Date Posted] :2022-04-25 16:28:51 ********COMMENT 4 ***** Reply From Stephen : as discussed. They have now provided the account nos. [Date Posted] :2022-05-05 17:07:09 ********COMMENT 5 ***** Reply From Stephen : 00422504735201 0010202430001 [Date Posted] :2022-05-05 17:09:47 | ISAAC WILSON | Robert Williams | Stephen Yao Agbeli | Unable To Recieve Alerts | 3 | SIB Bank Liberia | 20 days
10 | 2022-04-21 14:44 | IN00006408 | REQUEST ON REPORT | Please team we request a setup of monthly report on the following 1.Number of newly created users 2. Number of disabled users 3. Number of Service accounts ( X100 ) 4. Number of Password Reset 5. Number of users/roles in the Database 6. Total number of privileged database users 7. Number of backend access to database by privilege users? | Mohamed S. Conteh | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-21 15:41:08 ********COMMENT 2 ***** Reply From Nii Ayi : Hamza please follow up, some of the reports already exists. get scripts from Isaac to design a front end report. meanwhile i believe those given the database login access should be able to write scripts to get this basic reports [Date Posted] :2022-04-21 16:39:19 ********COMMENT 3 ***** Reply From Hamza Alieu : Ok Boss. Noted [Date Posted] :2022-04-22 09:58:13 ********COMMENT 4 ***** Reply From Hamza Alieu : Ok Boss. Noted [Date Posted] :2022-04-22 10:30:08 | Hamza Alieu Sesay | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 21 days
11 | 2022-04-20 10:26 | IN00006404 | EOD ERROR | IMBALANCE (VENDOR PAYMENT) | Director Amidu Sesay | ********COMMENT 1 ***** Reply From Prince : Investigation is ongoing root cause will be uploaded shortly [Date Posted] :2022-04-20 10:28:39 ********COMMENT 2 ***** Reply From Helpdesk : Hello Naa, kindly help. [Date Posted] :2022-04-20 10:28:48 | Naa Ashianor | Prince Manu | Naa Ashianor | Finance | 3 | Union Trust Bank | 22 days
12 | 2022-04-19 18:14 | IN00006402 | CASH SHORTAGE ON ST. MARYS ATM | St. Maryâ€™s ATM has now been loaded with 160,000,000 since it started operation 29/03/2022. Total approved transaction from the switch is 94,630,000 and the remaining cash on the ATM is 66,370,000. However, ATM GL balance is showing 72,220,000. This indicates 5,850,000 shortage on the ATM. Kindly provide us with all approved transaction logs for St Maryâ€™s terminal for the period 29/03/2022 to date | Ibrahim M. Conteh | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-20 08:15:45 ********COMMENT 2 ***** Reply From Hamza Alieu : Investigations still ongoing [Date Posted] :2022-05-03 08:44:04 | Nii Ayi Welbeck | TAMBA MOHAMED SANDY | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 23 days
13 | 2022-04-19 15:42 | IN00006401 | TELLERS CANNOT SEE ACCOUNT NOTES MADE ON ACCOUNTS. | Tellers cannot see Account Notes made on accounts but can be seen by other staffs that are not tellers. | Denco Wennie | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-04-19 15:44:18 ********COMMENT 2 ***** Reply From Stephen : as discussed [Date Posted] :2022-04-20 10:59:45 | ISAAC WILSON | Robert Williams | Stephen Yao Agbeli | Cash Operation / Teller | 3 | SIB Bank Liberia | 23 days
14 | 2022-04-19 12:28 | IN00006399 | CASH IN ATM- MAKENI | Based on your enquiry made this morning, there is a discrepancy of Le 2,100,000 between the ATM system cash and physical cash at Makeni Branch as at 18th April 2022 . | Mariama Kallon | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-19 13:15:58 ********COMMENT 2 ***** Reply From Nii Ayi : Hamza kindly update this ticket [Date Posted] :2022-04-21 16:41:34 ********COMMENT 3 ***** Reply From Hamza Alieu : Investigation is ongoing [Date Posted] :2022-04-26 19:28:41 | Hamza Alieu Sesay | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 23 days
15 | 2022-04-13 17:26 | IN00006393 | VULNERABILITY SCANNING | Kindly see attached document from InfoSec for your action. Audit also has raised this as an exception. Kindly treat with urgency. | Habib Conteh | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-14 08:24:41 ********COMMENT 2 ***** Reply From Nii Ayi : Danny for your attention please [Date Posted] :2022-04-18 12:21:59 ********COMMENT 3 ***** Reply From Hamza Alieu : . [Date Posted] :2022-04-25 15:58:21 | Daniel Nii Ayi Hammond | Mohamed L Jalloh | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 29 days
16 | 2022-04-12 16:59 | IN00006386 | DATABASE USERS INFOSEC | Please raise a ticket for the creation of the following InfoSec DB users. Bintu Jonah: bfjonah Mohamed Conteh: msconteh | Bintu Jonah | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-13 08:22:28 ********COMMENT 2 ***** Reply From Nii Ayi : Solo please get these users created, approval given by Dan already. [Date Posted] :2022-04-13 11:48:22 ********COMMENT 3 ***** Reply From Hamza Alieu : Solo kindly change ticket status [Date Posted] :2022-04-25 16:01:21 | Solomon Asante | Mohamed L Jalloh | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 30 days
17 | 2022-04-11 16:55 | IN00006381 | ATM IMBALANCE MAKENI | There is a cash difference between ATM physical cash and the GL in the amount Le 4,070,000 ( four million and seventy thousand Leones) Please find attached GL statement. | MARIAMA KALLON | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-12 08:09:19 ********COMMENT 2 ***** Reply From Nii Ayi : The attached file can not be accessed, meanwhile checks done reveals that the balance on the GL is correct per transaction posted by the ATM. any difference in cash should be reviewed physically. [Date Posted] :2022-04-13 12:06:28 | Nii Ayi Welbeck | Mohamed L Jalloh | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 31 days
18 | 2022-04-11 12:33 | IN00006379 | USSD REPORT CREATION | We kindly request a transactional report (excel and pdf) created for the below USSD Mobile Banking transactions. i. Bank to Wallet ii. Wallet to Bank iii. Airtime Purchase iv. Bill Payment v. Interbank Transfers The report should be created under Utilities- Report - Central Banking Channels | DANIEL | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-11 12:35:52 ********COMMENT 2 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-11 12:35:53 ********COMMENT 3 ***** Reply From Nii Ayi : Gadiel kindly liaise with the channels to get above reports, treat as a new project [Date Posted] :2022-04-11 18:31:40 ********COMMENT 4 ***** Reply From DANIEL : Please we need the below columns for the report; i. Posting Date ii. Narration iii. Customer Account number iv. Transaction Reference number v. Commission v. Transaction Count and Total transactional amount Please the search date should be limited to posting date. [Date Posted] :2022-04-14 09:15:43 ********COMMENT 5 ***** Reply From DANIEL : Columns needed; Posting Date, Account Number, Narration, Reference Number, Transactional Amount, Commission Kindly include Count and Total Amount at the end of the table [Date Posted] :2022-04-25 08:57:49 | Gaddiel Essuman-Acquah | DANIEL KORANTENG | Nii Ayi Welbeck | Others | 3 | Best Point | 31 days
19 | 2022-04-07 10:54 | IN00006373 | FWD: CASH IN TRNSIT | Our trail of mail refers. Our cash in transit keeps multiplying everyday. We kindly request that you clear the multiplied figures. | Horatia C. Godwin-Johnson | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayii, kindly help. [Date Posted] :2022-04-07 10:54:58 ********COMMENT 2 ***** Reply From Nii Ayi : I have made a request for the screen shots again for the current business date to understand the issue, Silla kindly honor this request. [Date Posted] :2022-04-10 19:12:26 ********COMMENT 3 ***** Reply From Mohamed : This issue has not been resolved successfully. [Date Posted] :2022-04-22 13:40:23 ********COMMENT 4 ***** Reply From Mohamed : This issue has not been resolved successfully. [Date Posted] :2022-04-22 13:40:25 ********COMMENT 5 ***** Reply From Mohamed : This issue has not been resolved successfully. [Date Posted] :2022-04-22 13:40:26 ********COMMENT 6 ***** Reply From Hamza Alieu : Richard your attention needed here [Date Posted] :2022-04-26 19:32:04 ********COMMENT 7 ***** Reply From Hamza Alieu : Richard your attention needed here [Date Posted] :2022-05-03 08:41:50 | Richard Tawiah-Baddoo | Mr Momoh Konneh | Nii Ayi Welbeck | Back Office | 3 | SIERRA LEONE COMMERCIAL BANK | 35 days |  | Old speci cleared as requested | 2022-04-11 20:27 | speci inward app in queue after failing to received speci the same day
20 | 2022-03-30 12:13 | IN00006348 | RE: FWD: RE: ATM CASH INBALANCE | Dear Team, Kindly see below differences for WRB and Roy ATMs as at 30th March, 2022. PHYSICAL SYSTEM DIFFERENCE ROY ATM 400,000.00 15,250,000.00 14,850,000.00 WRB ATM 81,290,000.00 89,550,000.00 8,260,000.00 Kindly help to resolve as these differences has prolonged and we are approaching end of month. | Neneh F. Dumbuya | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii, kindly help. [Date Posted] :2022-03-30 12:16:06 ********COMMENT 2 ***** Reply From Nii Ayi : Investigation completed, affected transaction will be sent via mail for confirmation and reposting [Date Posted] :2022-04-10 20:08:18 ********COMMENT 3 ***** Reply From TAMBA : Dear Welbeck, Did you send the affected transaction via mail and to whom?. [Date Posted] :2022-04-26 11:06:09 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 43 days
21 | 2022-03-29 10:19 | IN00006341 | LOAN WRITE OFF REPORT | Please find attached report for the earlier loan write offs done in the past to guide in designing the current report. As indicated to you earlier on, the current report does not show the amount written off in terms of interest and penalty. And even the principal written off is not clear. | Christian Ashun | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-03-29 10:27:23 ********COMMENT 2 ***** Reply From Nii Ayi : please do the necessary adjustments for this report as per request [Date Posted] :2022-04-07 10:35:41 | ALEX AGYEI | Christain Ashun | Nii Ayi Welbeck | Loans | 3 | Best Point | 44 days
22 | 2022-03-28 17:04 | IN00006338 | ISSUE THE APP SERVER SERVICES | We have realized that the App Server is not working as expected. | DAN | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-03-29 08:23:34 ********COMMENT 2 ***** Reply From Helpdesk : Solo, kindly help. [Date Posted] :2022-03-30 14:58:08 | Solomon Asante | DANIEL BLANKSON | Nii Ayi Welbeck | Back Office | 3 | EQUITY SAVINGS AND LOANS | 45 days
23 | 2022-03-28 11:34 | IN00006331 | CUSTOMER STATIC DATA | UPDATE ON CUSTOMER STATIC DATA DOES NOT REFLECT ON THE MOBILE APP REGISTRATION FORM. KINDLY ASSIST US. | K. ANTWI | ********COMMENT 1 ***** Reply From Helpdesk : Hello Naa, kindly help. [Date Posted] :2022-03-28 11:37:00 ********COMMENT 2 ***** Reply From Naa : Kwame, kindly give us the details that were updated and not reflecting [Date Posted] :2022-03-28 12:23:00 ********COMMENT 3 ***** Reply From Naa : Kwame, we are still waiting for the information [Date Posted] :2022-03-29 13:58:39 | Naa Ashianor | Kwame Antwi | Naa Ashianor | Others | 3 | Atwima Kwanwoma | 45 days
24 | 2022-03-24 17:44 | IN00006329 | ATM SYTEM ERROR | sir, Please investigate and kindly rectify difference in Mobimbi Branch ATM Cash as indicated below as at 24/03/2022 System Cash ........7,470,000 Physical Cash........ 360,000 Difference...............7,110,000 Regards Claudius | Claudius Taylor | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-03-24 22:15:51 ********COMMENT 2 ***** Reply From Mohamed : No, this issue has not been resolved. [Date Posted] :2022-04-19 10:21:20 ********COMMENT 3 ***** Reply From Hamza Alieu : Investigations still ongoing [Date Posted] :2022-05-03 08:42:50 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 49 days |  | Transactions posted manually | 2022-03-28 17:19 | Upgrade cause interruption, which causes transactions to hang
25 | 2022-03-24 17:10 | IN00006328 | NETWRIX USER CREATION | Infosec requested for Netwrix user in the X100+ database please see signed request form attacted. | Bintu Jonah | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-03-24 22:16:26 ********COMMENT 2 ***** Reply From Hamza Alieu : Waiting for database access to be worked on [Date Posted] :2022-04-06 10:20:06 ********COMMENT 3 ***** Reply From Hamza Alieu : Solo please take it from here [Date Posted] :2022-04-19 14:09:36 ********COMMENT 4 ***** Reply From Hamza Alieu : Solo kindly change ticket status [Date Posted] :2022-04-25 16:01:47 | Solomon Asante | SILLAH | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 49 days
26 | 2022-03-23 12:15 | IN00006319 | RE: SYSTEM NOT CHARGING SOME CUSTOMERS FOR VISA CARD MONTHLY MAINTANENCE FEES AND ATM FEES | Have included the date cards were issued to customers and it is expected that Maintenance fees are charged after cards have been issued to customers and are also charge ATM fees on withdrawals. | Bai Mansaray | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-03-23 12:16:41 ********COMMENT 2 ***** Reply From Nii Ayi : Hamza kindly liaise with Jude to investigate and act on this issue [Date Posted] :2022-03-24 12:46:09 ********COMMENT 3 ***** Reply From Hamza Alieu : Ok Sir noted [Date Posted] :2022-03-24 14:46:28 ********COMMENT 4 ***** Reply From Momoh : NOT RESOLVED [Date Posted] :2022-04-05 15:27:04 ********COMMENT 5 ***** Reply From Nii Ayi : Still investigating [Date Posted] :2022-04-07 10:28:05 | Nii Ayi Welbeck | Mr Momoh Konneh | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 50 days |  | Charges applied manually | 2022-03-28 17:24 | Upgrade cause interruption, which causes transactions to hang
27 | 2022-03-21 08:47 | IN00006310 | TELLER COUNTER CHECKS NOT GOING FOR APPROVAL. | Teller Counter Checks are not going for approval to the Branch Manager as usual. | All Tellers | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-03-21 08:49:33 ********COMMENT 2 ***** Reply From Stephen : Hi Robert, Kindly share user id for few of the tellers.. [Date Posted] :2022-03-21 11:33:12 ********COMMENT 3 ***** Reply From Stephen : As discussed [Date Posted] :2022-03-22 11:05:05 ********COMMENT 4 ***** Reply From Stephen : Isaac, this is the sample id..TELLER: VDALIEH [Date Posted] :2022-03-22 11:09:20 ********COMMENT 5 ***** Reply From Stephen : Dear Ernest/Okoro Audit would like to bring to your attention that, a teller can initiate and approve a transaction in the system irrespective of the amount involved for example on 26 April 2022 a customer was issued with a counter -cheque with an amount of USD2,000. This amount was above the tellers limit, however a teller by name Grace Borbor initiated approved the transaction at the Main Branch without approval from higher authority This could be attributed to system flaw. IT Department should ensure that this anomaly in the system is resolved with immediate effect [Date Posted] :2022-05-12 08:38:31 | ISAAC WILSON | Robert Williams | Stephen Yao Agbeli | Cheque Processing | 3 | SIB Bank Liberia | 52 days
28 | 2022-03-18 16:19 | IN00006308 | EOD ERROR. | EOD ERROR | Ernest Bediako | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen kindly help. [Date Posted] :2022-03-18 16:22:58 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-03-18 16:25:44 ********COMMENT 3 ***** Reply From Stephen : Hi Robert, kindly confirm if it is resolved.... [Date Posted] :2022-03-21 08:01:11 | Richard Tawiah-Baddoo | Robert Williams | Stephen Yao Agbeli | End of Day | 3 | SIB Bank Liberia | 55 days
29 | 2022-03-09 12:13 | IN00006271 | UTB MERCHANT PORTAL ISSUES | Issues: To login to the portal after a successful logout is an issue; the system dialog reports invalid login credentials Trying to reset merchant password from X100+ is not successful; please see attached page To reset the password on the merchant portal (forgot password) this option sends a "password reset link" by email and SMS but the link fails to connect to the password change page. | Joseph Mansaray | ********COMMENT 1 ***** Reply From Helpdesk : Hello Naa, kindly help [Date Posted] :2022-03-09 12:15:20 ********COMMENT 2 ***** Reply From Naa : FYA [Date Posted] :2022-03-09 12:47:25 ********COMMENT 3 ***** Reply From Daniel Nii Ayi : @Joshua T kindly assist [Date Posted] :2022-03-14 11:37:49 | Joshua Tetteh | Joseph Mansaray | Naa Ashianor | Others | 3 | Union Trust Bank | 64 days
30 | 2022-03-04 17:07 | IN00006262 | FIXED DEPOSIT PRE-LIQUIDATION | Hello Team, I kindly bring to your attention an anomaly with respect to Investment Pre-Liquidation. Our checks on some FD liquidations show that, the 70% pre-liquidation charge on the accrued interest is not automatically debit to the client accounts after liquidation. Find below two of such transactions that occurred today for your perusal; Client Name: Mary Asante FD A/C NO. 1401134032000 Certificate NO. 220105366 Client Name: Emelia Twum Ampofo FD A/C NO. 0700492533000 Certificate NO. 220125460 I have also attached a screen shot of the respective clients account. | Christian Ashun | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-03-06 12:41:30 ********COMMENT 2 ***** Reply From Nii Ayi : Emma for your attention [Date Posted] :2022-03-09 17:37:10 | Emmanuel Mantey | Christain Ashun | Nii Ayi Welbeck | Fixed Deposits | 3 | Best Point | 69 days
31 | 2022-03-04 15:58 | IN00006261 | TELLERS AT CLARA TOWNS BRANCH CAN DEPOSIT INTO A CERTAIN ACCOUNT. | The tellers at the Clara Towns branch can deposit into a particular account. The account number is: 0011120482020. | Charlesetta Jackson | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-03-04 16:03:20 ********COMMENT 2 ***** Reply From Stephen : Is it affecting only this account or all account ? [Date Posted] :2022-03-04 17:03:32 ********COMMENT 3 ***** Reply From Stephen : Is it affecting only this account or all account ? [Date Posted] :2022-03-04 17:03:37 ********COMMENT 4 ***** Reply From Robert : Resolved. [Date Posted] :2022-03-08 09:48:56 ********COMMENT 5 ***** Reply From Stephen : as discussed [Date Posted] :2022-03-08 12:23:48 ********COMMENT 6 ***** Reply From Stephen : . [Date Posted] :2022-03-08 12:25:05 ********COMMENT 7 ***** Reply From Stephen : Hi Richard, kindly provide the RCA and change the status to "RESOLVED" [Date Posted] :2022-03-17 08:38:12 ********COMMENT 8 ***** Reply From Robert : Resolved [Date Posted] :2022-04-05 09:14:05 | Richard Tawiah-Baddoo | Robert Williams | Stephen Yao Agbeli | Cash Operation / Teller | 3 | SIB Bank Liberia | 69 days
32 | 2022-02-28 12:50 | IN00006247 | CREATE USERS ON DEVOLPMENT SERVER (60) | Create users on the database and change password for bankowner on the development server. | USG | ********COMMENT 1 ***** Reply From Helpdesk : Hello Caleb, kindly help. [Date Posted] :2022-02-28 12:51:52 | CALEB AMARFIO | CALEB AMARFIO | USG | Others | 3 | USG | 73 days
33 | 2022-02-24 17:28 | IN00006237 | ISSUE WITH INBALANCES IN LEDGER AND VAULT POSITION (DOME AND ACCRA CENTRAL BRNCH) | After running end of day s at 23rd February, 2022, we have realized two of our branches ledger are not balancing. That is Dome and Accra central branch. Kindly investigate and restore. | Mercy | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii, kindly help. [Date Posted] :2022-02-25 08:31:07 ********COMMENT 2 ***** Reply From DANIEL : I have done Vault adjustment which has become normalcy now. [Date Posted] :2022-02-25 15:12:19 ********COMMENT 3 ***** Reply From Stephen : Thanks. Kindly check after EOD and provide the final comment.. [Date Posted] :2022-02-25 16:39:12 ********COMMENT 4 ***** Reply From Stephen : Thanks. Kindly check after EOD and provide the final comment.. [Date Posted] :2022-02-25 16:39:28 | Nii Ayi Welbeck | DANIEL BLANKSON | Nii Ayi Welbeck | Back Office | 3 | EQUITY SAVINGS AND LOANS | 77 days
34 | 2022-02-23 11:07 | IN00006229 | REVALUATION GAIN / LOSS - SLL-----133100000002 | We observed a debit in Revaluation Gain/loss SLL for review done as at 22nd Feb 2022 as shown below. Posting date Value date Trans. Details Document Ref Debit (SLL) 22-FEB-2022 22-FEB-2022 FX POSITION REVALUATION ADJUSTMENT 2022022222088 2,789,703,048.92 | ABDUL AZIZ KAMARA | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-02-23 11:08:29 ********COMMENT 2 ***** Reply From Nii Ayi : investigation underway for RCA [Date Posted] :2022-02-27 23:45:49 ********COMMENT 3 ***** Reply From Hamza Alieu : Prince kindly take action as this issue has been resolved. Thanks [Date Posted] :2022-04-04 18:03:41 ********COMMENT 4 ***** Reply From Hamza Alieu : Prince kindly take action as this issue has been resolved. Thanks [Date Posted] :2022-05-03 08:37:47 | Prince Manu | Mr Momoh Konneh | Nii Ayi Welbeck | Finance | 3 | SIERRA LEONE COMMERCIAL BANK | 78 days
35 | 2022-02-15 09:56 | IN00006195 | ON THE CREDIT ORIGINATION SCREEN, THE BANK SHOULD HAVE THE ABILITY TO SELECT THE EXEMPTION MONTHS. BUT IT IS PRESENTLY TIED TO JULY & DECCEMBER ONLY. | On the credit origination screen, the bank should have the ability to select the exemption months. But it is presently tied to July & Deccember only. | William / Ernest | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-02-15 09:58:53 ********COMMENT 2 ***** Reply From Kofi Agbexwe : Assigned to Agyei Alex [Date Posted] :2022-02-15 15:43:32 | ALEX AGYEI | Stephen Yao Agbeli | Stephen Yao Agbeli | Loan / Credit | 3 | SIB Bank Liberia | 86 days
36 | 2022-02-14 13:28 | IN00006179 | ACCOUNT MANDATE UPDATE & MANDATE CARDS (NOT SHOWING/DISAPPEARING) | 1. Account mandate update for some specific accounts not showing 2. Mandate Cards for some specific accounts disappearing | DENCO / ERNEST | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-02-14 13:30:49 ********COMMENT 2 ***** Reply From Stephen : Sample accounts requested from Operations head. SIB to provide [Date Posted] :2022-02-14 13:33:18 ********COMMENT 3 ***** Reply From Stephen : Issue worked on. Kindly check and confirm.... [Date Posted] :2022-03-08 15:57:41 ********COMMENT 4 ***** Reply From Stephen : Reply From : Stephen Status: (WORK IN PROGRESS) 2022-03-08 15:57:41 Issue worked on. Kindly check and confirm.... [Date Posted] :2022-05-09 11:34:35 | Stephen Yao Agbeli | Stephen Yao Agbeli | Stephen Yao Agbeli | Signature | 3 | SIB Bank Liberia | 87 days
37 | 2022-02-10 13:27 | IN00006171 | ISSUE WITH CASHBACK LOAN DOES NOT ACCRUED PENALTY. | We have realized the Cash Back loan does not accrued penalty when a client default. | Khalid | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-02-10 13:29:34 ********COMMENT 2 ***** Reply From Stephen : [1:36 PM, 2/10/2022] STEPHEN YAO AGBELI: Kindly provide 1 sample account.. [1:39 PM, 2/10/2022] Equity Daniel: 075590177001 [Date Posted] :2022-02-10 13:41:33 | Nii Ayi Welbeck | DANIEL BLANKSON | Nii Ayi Welbeck | Loan / Credit | 3 | EQUITY SAVINGS AND LOANS | 91 days
38 | 2022-02-10 11:40 | IN00006167 | CASH WITHDRAWAL TIME FOR APPROVAL AND POSTING TIME ARE THE SAME | Cash withdrawal time for approval and posting time are the same | OTIS | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help [Date Posted] :2022-02-10 11:41:21 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-10 12:30:28 ********COMMENT 3 ***** Reply From Stephen : about 73.24% through.. [Date Posted] :2022-05-10 14:59:37 | Gaddiel Essuman-Acquah | Stephen Yao Agbeli | Stephen Yao Agbeli | Cash Operation / Teller | 3 | SIB Bank Liberia | 91 days
39 | 2022-02-10 11:30 | IN00006166 | WE ARE ALSO EXPERIENCING A SCANNER WITH 32 PAGES OR MORE | We are also experiencing a scanner with 32 pages or more scan will read for more than 20 minutes to generate a token amidst promises of scanning 1,000 pages in 1 minute. | Mohammed Alie Kamara | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help [Date Posted] :2022-02-10 11:30:22 ********COMMENT 2 ***** Reply From Helpdesk : Elijah, kindly help. [Date Posted] :2022-02-10 11:32:17 | ELIJAH ASHITEY | Union Issues Management Team | Nii Ayi Welbeck | Back Office | 3 | Rokel Commercial Bank | 91 days
40 | 2022-02-10 09:09 | IN00006161 | LARGE EXCELL FORMATTING VERY DIFFICULT | Large Excell formatting very difficult | Macarr / ERNEST | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-02-10 09:10:05 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-10 10:04:16 | Emmanuel Mantey | Stephen Yao Agbeli | Stephen Yao Agbeli | Online Reports | 3 | SIB Bank Liberia | 91 days
41 | 2022-02-09 15:22 | IN00006156 | TELLER TRANSACTION COUNT REPORT - REPORT CODE ABIN & ABIQ | Teller transaction count report - Report code ABIN & ABIQ (USG to investigate ) | Miss George/Zinnah | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-02-09 15:24:43 ********COMMENT 2 ***** Reply From Stephen : fya [Date Posted] :2022-02-09 16:42:06 | Gaddiel Essuman-Acquah | Stephen Yao Agbeli | Stephen Yao Agbeli | Online Reports | 3 | SIB Bank Liberia | 92 days
42 | 2022-02-08 18:10 | IN00006151 | REQUEST FOR STR REPORT | Request for STR Report | Brima B. Sannoh | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2022-02-09 08:23:31 ********COMMENT 2 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-02-09 09:47:57 ********COMMENT 3 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-09 10:44:29 | Gaddiel Essuman-Acquah | Stephen Yao Agbeli | Stephen Yao Agbeli | Others | 3 | SIB Bank Liberia | 93 days
43 | 2022-02-08 17:44 | IN00006150 | MOBILE APP & INTERNET BANKING(PERSONAL) ISSUES AND REQUEST | "ATM Card Request - Mobile App & Internet Banking(Personal). Integrate ATM Card Request Registration in the Mobile App. Replicate ATM Request Form Code (ATAA) in the Mobile app to allow Customers Request for ATM Cards without coming to the Branch. This is intended to reduce the Human interaction at the Branches" Internet Banking - Mobile App Self Enrollment not charged monthly internet banking fees. Apply Charges | Zinnah Smith-Samuels / Ernest | ********COMMENT 1 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-08 17:46:02 ********COMMENT 2 ***** Reply From Helpdesk : Issue to be converted to project... [Date Posted] :2022-02-16 17:03:14 ********COMMENT 3 ***** Reply From Stephen : Update on the ATM card Request: USG is ascertaining the most appropriate way to implement the ATM request forms on the mobile app and internet banking platform. Also USG to make available ATM request APIs on both platforms.. The target date is 31/03/2022 [Date Posted] :2022-03-01 11:29:49 ********COMMENT 4 ***** Reply From Stephen : Update on the ATM card Request: USG is ascertaining the most appropriate way to implement the ATM request forms on the mobile app and internet banking platform. Also USG to make available ATM request APIs on both platforms.. The target date is 31/03/2022 [Date Posted] :2022-03-01 11:30:10 | JONATHAN ATO MARKIN | Stephen Yao Agbeli | Stephen Yao Agbeli | Atm Card Request | 3 | SIB Bank Liberia | 93 days
44 | 2022-02-08 11:29 | IN00006143 | DATABASE AUDIT REPORT | Database audit report | Otis W. Doe / ERNEST | ********COMMENT 1 ***** Reply From Stephen : As discussed on whatsapp [Date Posted] :2022-02-08 11:29:48 ********COMMENT 2 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-02-08 11:31:30 ********COMMENT 3 ***** Reply From Stephen : As discussed on whatsapp [Date Posted] :2022-02-08 12:38:50 | Solomon Asante | Stephen Yao Agbeli | Stephen Yao Agbeli | Others | 3 | SIB Bank Liberia | 93 days
45 | 2022-02-04 10:16 | IN00006131 | ISSUE WITH GLOBAL USER AND TRANS ENQ ACCESS AUTHORISATION | We cannot authorize Global user access and Trans inquiry access. | Dan | ********COMMENT 1 ***** Reply From Helpdesk : Nii, please help. [Date Posted] :2022-02-04 10:17:36 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-04 12:57:06 ********COMMENT 3 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-15 11:55:26 | Gaddiel Essuman-Acquah | DANIEL BLANKSON | Nii Ayi Welbeck | Back Office | 3 | EQUITY SAVINGS AND LOANS | 97 days
46 | 2022-02-03 11:55 | IN00006129 | MOBILE APP TRANSACTIONS | ACCOUNT # 1081120006646541 WAS ABLE TO WITHDRAW GHÂ¢198 ON HIS CURRENT ACCOUNT ON 02/02/2022. KINDLY HELP US INVESTIGATE AND RESOLVE TO AVOID FUTURE OCCURRENCES. | customer | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2022-02-03 11:58:05 ********COMMENT 2 ***** Reply From Naa : FYA [Date Posted] :2022-02-03 12:07:10 | Daniel Nii Ayi Hammond | Kwame Antwi | Naa Ashianor | Others | 3 | Atwima Kwanwoma | 98 days
47 | 2022-02-03 09:55 | IN00006126 | RE: CASH IMBALANCE AT ATM WILKINSON BRANCH | Good morning team, Please be informed that we still have a difference of Le1,910,000.00 at Roy ATM and Le3,300,000.00 at Wilkinson Road ATM. Please help us rectify this difference as it occurred due to the system challenge we encountered on Friday. Both ATMs were checked and balanced in the morning hours of Friday, 28th January, 2022 only to discover a difference on Monday, 31st January. Regards | Neneh F. Dumbuya | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-02-03 10:00:31 ********COMMENT 2 ***** Reply From Nii Ayi : For your attention [Date Posted] :2022-02-18 14:55:13 ********COMMENT 3 ***** Reply From Mohamed : This issue has not been resolved. [Date Posted] :2022-04-19 12:01:43 ********COMMENT 4 ***** Reply From Hamza Alieu : Investigations still ongoing [Date Posted] :2022-05-03 08:43:25 | Nii Ayi Welbeck | Mohamed Kabba Kamara | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 98 days |  | Transactions reposted to help balance ATM GL | 2022-02-22 18:28 | Space issue on db
48 | 2022-01-25 11:39 | IN00006087 | ISSUE WITH TRANSACTION ENQUIRY PRINTING | Transaction enquiry screen is giving error when printing report or exporting in to excel: "REP-56048: Engine rwEng-0 crashed., job Id: 110643" | Christian Ashun | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-01-25 12:08:17 ********COMMENT 2 ***** Reply From Stephen : As discuss, kindly assist.. [Date Posted] :2022-01-25 13:09:24 | Gaddiel Essuman-Acquah | Christain Ashun | Nii Ayi Welbeck | Operations | 3 | Best Point | 107 days
49 | 2022-01-21 16:46 | IN00006069 | RTGS AUTOMATED RECONCILIATIONS | RTGS automated RECONCILIATIONs not available or unseen. Extend this to cover ALL Auto Reconciliable Accouints. | Willie Johnson | ********COMMENT 1 ***** Reply From Helpdesk : Please handle [Date Posted] :2022-01-21 18:55:44 | Jude Kuwornu | Union Issues Management Team | Nii Ayi Welbeck | RTGS | 3 | Rokel Commercial Bank | 111 days
50 | 2022-01-17 10:52 | IN00006057 | MODEL FOR CHQ BK SERIAL NUMBERS | Please we request that you assist us include a column in the X100 CHQ BOOK requisition model to enable CSOs enter the last cheque book serial numbers when making a new requisition. This we believe would help mitigate the issues of repetitive cheque book serial numbers. Counting on your usual support | David F. Sackeyfio | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-01-17 10:53:18 ********COMMENT 2 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2022-01-17 10:53:56 ********COMMENT 3 ***** Reply From Stephen : fya [Date Posted] :2022-01-17 16:41:42 ********COMMENT 4 ***** Reply From Stephen : fya [Date Posted] :2022-02-15 09:02:19 ********COMMENT 5 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-15 11:53:00 | Gaddiel Essuman-Acquah | David F. sackeyfio | Nii Ayi Welbeck | Cheque Processing | 3 | Best Point | 115 days
51 | 2022-01-14 14:19 | IN00006053 | OFFICIAL ACCOUNT STATEMENTS PRINTED ARE BEING OVER CHARGED | Official Account Statements Printed are being over Charged. That is, there is always an overstatement of the number of pages printed from the system. For instance, whilst the system might have stated and charged 3 pages, after issuing the print command, the print-out that came were only 2 pages. This is also happening across all the branches. 1. Michael Hanson 0312270090500 2. Emmanuel Odarkwei Mills 0712260153201 | Mercy | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-01-14 14:20:37 ********COMMENT 2 ***** Reply From Stephen : fya [Date Posted] :2022-01-17 16:42:27 ********COMMENT 3 ***** Reply From Stephen : fya [Date Posted] :2022-02-10 17:08:11 | Gaddiel Essuman-Acquah | DANIEL BLANKSON | Nii Ayi Welbeck | Back Office | 3 | EQUITY SAVINGS AND LOANS | 118 days
52 | 2022-01-11 17:16 | IN00006039 | BRANCHES ARE NOT RISK RATING USING THE RISK CALCULATOR. THE RISK CALCULATOR SHOULD BE MANDATORY. THE SYSTEM SHOULD NOT ALLOW THEM TO PROCEED IF THEY HAVE NOT RISK RATED THE CUSTOMER. | On the account opening portal the risk rating already obtained should be used on the Anti Money laundering Risk code. | Jennifer Jonah | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-01-12 10:09:58 | Nii Ayi Welbeck | Jonah Onesimus | Nii Ayi Welbeck | Operations | 3 | Rokel Commercial Bank | 121 days
63 | 2022-01-11 09:42 | IN00006036 | WE WRITE TO REPORT THAT THERE IS A DEBIT BALANCE OF LE822,803,433.82 SITTING IN RCB CLEARING SUSPENSE ON THE BRANCH | We write to report that there is a debit balance of Le822,803,433.82 sitting in RCB clearing suspense on the branch Trial Balance since the 28th December 2021. However, the RCB clearing GL account 121100000001 is showing a nill balance consistently since that date. Kindly investigate and resolve accordingly. See attached RCB clearing Suspense and branch Trial Balance for ease of reference. | YUSUF SHERIFF | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-01-11 09:56:05 ********COMMENT 2 ***** Reply From Mohamed : It been more than 6 day now and we are still waiting on a resolution on this issue and the client is callin g everyday to check, Please what the way forward..? [Date Posted] :2022-01-18 10:21:47 ********COMMENT 3 ***** Reply From Hamza Alieu : . [Date Posted] :2022-04-04 18:10:59 ********COMMENT 4 ***** Reply From Mohamed : We are still waiting on a resolution on this issue and the client is calling. [Date Posted] :2022-04-07 17:45:08 ********COMMENT 5 ***** Reply From Hamza Alieu : Prince this issue is still pending for your action [Date Posted] :2022-05-03 08:39:32 | Prince Manu | Mohamed L Jalloh | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | 121 days
64 | 2021-12-30 09:36 | IN00005993 | TELLER TRANSACTION DATE AND TIME ISSUE. | Date and time for teller transactions that goes for approval are the same. That is, the request date is the same as the approval date. Kindly help us fix the issue ASAP. Thank you. | Christian Ashun | ********COMMENT 1 ***** Reply From Stephen : FYA [Date Posted] :2021-12-30 09:43:53 ********COMMENT 2 ***** Reply From Stephen : As discussed [Date Posted] :2022-02-10 12:29:27 | Gaddiel Essuman-Acquah | Christain Ashun | Nii Ayi Welbeck | Operations | 3 | Best Point | 133 days
65 | 2021-12-15 14:02 | IN00005973 | BIOMETRIC VERIFICATION REPORT | Kindly help us with a script that we can use in pulling a report on biometric verification for transactions at the branches. | Christian Ashun | ********COMMENT 1 ***** Reply From Stephen : fya.. [Date Posted] :2021-12-15 15:28:15 ********COMMENT 2 ***** Reply From Stephen : Hi Chris. The team has started work on your request. The following are being looked at. A. Details to be captured B. Storage of captured details C. Modification/design of forms. ( If necessary) D. Script for the report.. [Date Posted] :2022-01-24 09:45:22 ********COMMENT 3 ***** Reply From Stephen : The team is targeting close of this week to complete this. The report will capture transactions done after the implementation and not transactions done before implementation.. [Date Posted] :2022-02-07 15:33:25 ********COMMENT 4 ***** Reply From Stephen : System implemented. UAT and UVT signed off... [Date Posted] :2022-02-22 11:18:30 | Richard Tawiah-Baddoo | Christain Ashun | Nii Ayi Welbeck | Operations | 3 | Best Point | 148 days
66 | 2021-12-01 05:54 | IN00005955 | OVERDRAWN SUSU ACCOUNT -MOBILE APP CHANNEL | ACCOUNT # 1081210006474941 WAS ABLE TO WITHDRAW GHÂ¢500 ON HIS SUSU ACCOUNT ON 22/11/2021 TIME: 23:34 WHEN THE AVAILABLE BALANCE WAS GHÂ¢6.00 THROUGH THE MOBILE APP DURING THE EOD PROCESS. KINDLY HELP US INVESTIGATE AND RESOLVE TO AVOID FUTURE OCCURRENCES. | CUSTOMER | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2021-12-01 14:29:30 ********COMMENT 2 ***** Reply From Kwame : Pls can we get any update on this issue [Date Posted] :2021-12-08 17:51:38 ********COMMENT 3 ***** Reply From Naa : FYA [Date Posted] :2021-12-09 08:17:52 | JONATHAN ATO MARKIN | Kwame Antwi | Naa Ashianor | Funds Transfer | 3 | Atwima Kwanwoma | 162 days
67 | 2021-11-25 08:24 | IN00005916 | USSD EXCEPTION DAILY LIMIT INCREMENT | We kindly request a screen to be developed for customers to request for USSD daily limit increment. Currently the daily limit for all customers is 2000 cedis but there is no way a customer can opt to increase the preset limit. Kindly assist | Daniel/Nana Adu | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2021-11-25 09:09:35 ********COMMENT 2 ***** Reply From Stephen : fya [Date Posted] :2021-11-28 22:31:50 ********COMMENT 3 ***** Reply From DANIEL : Please no work done on this yet? Kindly let us expedite on it. [Date Posted] :2022-01-17 09:12:23 ********COMMENT 4 ***** Reply From DANIEL : Dear support, please this issue is still pending and it has been over months now. Kindly treat as urgent as there is a high demand for this service [Date Posted] :2022-04-05 13:59:37 ********COMMENT 5 ***** Reply From DANIEL : Please we are still on standby as there is a high demand for this function. [Date Posted] :2022-04-25 10:08:20 | Daniel Nii Ayi Hammond | DANIEL KORANTENG | Nii Ayi Welbeck | Others | 3 | Best Point | 168 days
68 | 2021-11-24 17:56 | IN00005915 | END OF DAY PROCESS TOO LONG | End of Day Proces takes too long to complete. It lasts for approximately 6 and half hours daily from Pre EOD Backup to Post EOD Backup. Kindly investigate | Sallieu Kabba; Joseph Mansaray | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2021-11-24 18:52:40 ********COMMENT 2 ***** Reply From Naa : FYA [Date Posted] :2021-11-30 12:05:03 ********COMMENT 3 ***** Reply From Solomon : Thank you for reaching out with me, kindly get me pre-eod-backup and post-eod-backup logs as at 29 November, 2021. [Date Posted] :2021-11-30 12:39:29 | Solomon Asante | Joseph Mansaray | Naa Ashianor | End of Day | 3 | Union Trust Bank | 169 days
69 | 2021-11-16 12:41 | IN00005899 | ISSUE WITH SMS ALERT | The customers with details below do not receive sms alert even though they have been signed up. Name: Tinabel Ofori Account number: 0311110003300 Telephone number: 0242331616 Name: Mabel Abra Bani Account Number: 0312260104400 Telephone Number: 0246824706 Standing by for swift response. | Dan | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2021-11-17 07:57:18 ********COMMENT 2 ***** Reply From Stephen : Outbound SMS Delivered - No errors No Error (code 0) Reason: DELIVERED_TO_HANDSET Nov 16, 12:58:32 Equity Nov 16, 13:00:39 233242331616 [Date Posted] :2021-11-17 08:48:07 ********COMMENT 3 ***** Reply From Stephen : [13:15, 11/16/2021] Equity Daniel: But whenever there is transaction on that account she doesn gets alert.... [13:16, 11/16/2021] STEPHEN YAO AGBELI: Check the setup as well.. Setup to receive SMS [Date Posted] :2021-11-17 08:48:54 | Nii Ayi Welbeck | DANIEL BLANKSON | Nii Ayi Welbeck | Unable To Recieve Alerts | 3 | EQUITY SAVINGS AND LOANS | 177 days
70 | 2021-11-09 11:26 | IN00005885 | CASH MOVEMENT INWARD -SINKOR BRANCH | Mail from Finance Manager(BAYSAH CLARENCE): "Dear Ernest, We have suspected some technical issue with Johns profile used to post transactions that debit and credit are not in agreement John is not aware of the posting in the system. Kindly review the system. | baysah Clerence | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2021-11-09 11:29:42 ********COMMENT 2 ***** Reply From Stephen : The following required please... 1. Ref. no 2. Date and 3. Johns Profile [Date Posted] :2021-11-09 11:32:27 ********COMMENT 3 ***** Reply From Stephen : Hi Rich, As discussed, kindly provide your findings.. [Date Posted] :2021-11-11 09:21:33 ********COMMENT 4 ***** Reply From Stephen : . [Date Posted] :2022-03-08 12:31:35 | Richard Tawiah-Baddoo | Ernest Mensah Bediako | Stephen Yao Agbeli | Others | 3 | SIB Bank Liberia | 184 days
71 | 2021-11-04 06:48 | IN00005876 | OUT DATED SOFTWARES | VAPT test conducted reveals we e running out Apache and PHP on the following servers; we recommend 10.7.22.66 -MobiCollect Server -Apache Tomcat outdated 10.7.22.79- ORASS Server - Apache Tomcat outdated / PHP 10.7.22.87 Image Server - Apache Tomcated Outdated / PHP Framework Outdated | KWAME ANTWI | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2021-11-04 08:00:26 ********COMMENT 2 ***** Reply From Naa : it will be better to upgrade your current system. awaiting your feedback [Date Posted] :2021-11-05 20:30:17 | Naa Ashianor | Kwame Antwi | Naa Ashianor | Others | 3 | Atwima Kwanwoma | 189 days
72 | 2021-10-22 09:57 | IN00005839 | ATM CARD REQUISITION IS POSSIBLE EVEN WHEN THERE IS AN EXISTING ACTIVE CARD ON THE ACCOUNT. | ATM Card requisitions have been duplicating in the system for accounts with existing ATM cards. This causes the card printing exercise to be halted. We request that when a card is issued on an account, re issuance is only made possible when the existing card is disabled in X100+. This should be deployed at both card request channels; Mobile App, and at the branch. | Alex Koroma | ********COMMENT 1 ***** Reply From Helpdesk : Naa, kindly help. [Date Posted] :2021-10-22 11:54:20 ********COMMENT 2 ***** Reply From Helpdesk : Danny, kindly help. [Date Posted] :2021-10-25 10:20:29 | Daniel Nii Ayi Hammond | BAIMBA BOCKARIE | Naa Ashianor | Others | 3 | Union Trust Bank | 202 days
73 | 2021-10-11 15:36 | IN00005820 | ACCOUNT MANDATE ISSUES | Please have noticed discrepancies in the customer account mandate, where Customer A details is showing Customer Bs mandate details. For example, this customer DZODJI AMUZU with customer number 0501750 and account number 1220050175000, has another customer mandate on his account. Same as this customer 1222010471200 ABENA KWARTEMAA. http://10.10.1.10:82/imaging/getimages-1220050175000 http://10.10.1.10:82/imaging/getimages-1222010471200 | Gabby | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kindly help. [Date Posted] :2021-10-11 15:37:40 ********COMMENT 2 ***** Reply From Stephen : Kindly let your team amend the discrepancies.. I am On standby for the outcome... [Date Posted] :2021-10-11 16:36:49 ********COMMENT 3 ***** Reply From IT ADMIN : Are you asking us to this manually or, these are just examples to show we noticed over a hundred [Date Posted] :2021-10-12 10:14:37 ********COMMENT 4 ***** Reply From Stephen : fya [Date Posted] :2021-10-12 17:31:08 ********COMMENT 5 ***** Reply From Stephen : Yes, amend them manually. Verification is required by the bank.. [Date Posted] :2021-10-13 09:19:16 ********COMMENT 6 ***** Reply From Jude : Please take a look at this [Date Posted] :2022-03-09 15:50:53 | Gaddiel Essuman-Acquah | IT ADMIN | Stephen Yao Agbeli | Signature | 3 | GOLDEN PRIDE | 213 days
74 | 2021-10-01 16:39 | IN00005771 | CUSTOMERS PICTURES/SIGNATURE NOT APPEARING AFTER UPDATE. | When the customer service officers do the update of an account and it has been approved and they try to view signature cards in X100, they would see no image. | Rania Goll, Dorothea Pettiquoi | ********COMMENT 1 ***** Reply From Helpdesk : Stephen, kndly help. [Date Posted] :2021-10-01 16:40:40 ********COMMENT 2 ***** Reply From Stephen : Fya.. [Date Posted] :2021-10-05 16:26:56 ********COMMENT 3 ***** Reply From Robert : How far, please. [Date Posted] :2021-10-12 10:40:56 ********COMMENT 4 ***** Reply From Robert : How far with this please. [Date Posted] :2021-10-18 09:46:43 ********COMMENT 5 ***** Reply From Stephen : Hi Robert, Can you provide the exact requirement.. ? [Date Posted] :2021-10-25 08:26:57 ********COMMENT 6 ***** Reply From Robert : After the customer service officer does the update of an account, no one can view the updated photo and signature of the account. [Date Posted] :2021-10-25 08:53:33 ********COMMENT 7 ***** Reply From Robert : How far with this issue? The thing here is that after the Customers Service Officers have done the update on any account, nobody is able to view the signature card or the updated picture. [Date Posted] :2021-10-29 09:31:01 ********COMMENT 8 ***** Reply From Robert : Please, customers are not being paid because of this. Please attach some urgency to this. [Date Posted] :2021-11-18 10:49:58 ********COMMENT 9 ***** Reply From Robert : This is still not resolved. [Date Posted] :2021-12-17 10:27:11 ********COMMENT 10 ***** Reply From Stephen : Hi Robert, kindly confirm if the signature is appearing.. [Date Posted] :2022-03-09 14:20:44 | ELIJAH ASHITEY | Robert Williams | Stephen Yao Agbeli | Customer Service | 3 | SIB Bank Liberia | 223 days
75 | 2021-09-03 08:44 | IN00005660 | ISSUE WITH THE SYSTEM CHANGING THE ID NUMBERS CAPTURED IN UPPER CASE TO LOAVWER CASE | We have observed that ID cards numbers that start with alphabets (Ghana Card, Business Registration, Drivers License and Passport) that have been captured in upper case, turn to be lower case output in the system(x100). Kindly change it to upper case. | Dan | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2021-09-03 08:56:21 ********COMMENT 2 ***** Reply From Nii Ayi : Character case in the table is still upper case but the for displays in lower case by default. currently form FMBs not available [Date Posted] :2022-04-07 10:18:50 | Nii Ayi Welbeck | DANIEL BLANKSON | Nii Ayi Welbeck | Back Office | 2 | EQUITY SAVINGS AND LOANS | 251 days
76 | 2021-04-13 11:42 | IN00005259 | FAILED CARDLESS TRANSACTION FAIL TO REVERSE | I have noticed when a cardless transaction fails, the transaction is not reversed, the commission is also not reversed. The transaction will just get missing and a manual reversal would be required. It happens mostly when we have no cash or cash jam transactions. | Director Sallieu Kabba | ********COMMENT 1 ***** Reply From Helpdesk : fya [Date Posted] :2021-04-13 12:04:56 ********COMMENT 2 ***** Reply From Naa : FYA [Date Posted] :2021-04-16 09:51:07 ********COMMENT 3 ***** Reply From Daniel Nii Ayi : We will need a sample request to see how the atm pass the automatic cardless reversal transactoin [Date Posted] :2021-07-22 15:50:42 | Daniel Nii Ayi Hammond | Joseph Mansaray | Naa Ashianor | Others | 2 | Union Trust Bank | 394 days
77 | 2021-03-09 14:07 | IN00005217 | DEBIT INTEREST (OVER-DRAFT) | Debit Interest Transaction was charged to the accounts again on March 01, 2021, overstating our loan figures. All these charges must be reversed to show the true loan portfolio figure. This was the issue which was resolve in January 2021. | Angela | ********COMMENT 1 ***** Reply From Helpdesk : Steve, kindly help. [Date Posted] :2021-03-09 14:08:28 ********COMMENT 2 ***** Reply From Helpdesk : Hi Derrick, kindly assist.. [Date Posted] :2021-03-11 07:32:51 ********COMMENT 3 ***** Reply From IT ADMIN : The issues have not been full reslove [Date Posted] :2021-08-18 10:58:37 ********COMMENT 4 ***** Reply From Stephen : Kindly look at the issue again. Client not satisfied [Date Posted] :2021-08-30 12:51:20 ********COMMENT 5 ***** Reply From Kofi Agbexwe : Assigned to you [Date Posted] :2021-08-30 15:25:00 ********COMMENT 6 ***** Reply From Kofi Agbexwe : Assigned to you [Date Posted] :2021-08-30 15:37:51 ********COMMENT 7 ***** Reply From Stephen : Kindly provide the account for the reversal.. [Date Posted] :2021-09-07 16:25:56 ********COMMENT 8 ***** Reply From IT ADMIN : This issue is well known by your staff and we are shocked they are asking for these details. [Date Posted] :2021-09-13 13:07:54 ********COMMENT 9 ***** Reply From Stephen : Kindly provide the account to enable them reverse the entry.. [Date Posted] :2021-09-13 14:43:57 ********COMMENT 10 ***** Reply From IT ADMIN : you requested for mail on this issue which was sent on the 28 of September. which clearly states your team was to provide us with those accounts since Febuary 2021. [Date Posted] :2021-10-11 10:04:44 ********COMMENT 11 ***** Reply From IT ADMIN : you requested for mail on this issue which was sent on the 28 of September. which clearly states your team was to provide us with those accounts since Febuary 2021. [Date Posted] :2021-10-11 10:06:52 | Nii Ayi Welbeck | IT ADMIN | Stephen Yao Agbeli | Loan / Credit | 1 | GOLDEN PRIDE | 429 days |  | this is listed as part of the golder pride cleanup exercise and updates are been sent to golden pride daily/weekly | 2021-06-06 17:13 | this is listed as part of the golder pride cleanup exercise and updates are been sent to golden pride daily/weekly
Resolved Issues
Id | Date_Logged | Ticket_Id | Incident_Summary | Incident_Details | Person_Affected | Comment | Technical Person | Logged By | Relations Manager | Affected_Area | Severity | Client_Name | Days_Pending | Status | Resolution_Details | Resolved_Date | Root_Cause
1 | 2022-05-09 12:57 | IN00006453 | X10 HAS BLOCKED A CERTAIN AMOUNT OF MONEY FROM AN ACCOUNT. | Seventy dollars and eighty seven cents has been blocked from the available balance of an account with number: 0111201852301 and name Skyward Xpress. | Denco Wennie | ********COMMENT 1 ***** Reply From Helpdesk : Hello Stephen, kindly help. [Date Posted] :2022-05-09 12:58:44 ********COMMENT 2 ***** Reply From Stephen : Kindly use the lien screen [Date Posted] :2022-05-09 13:21:51 | Stephen Yao Agbeli | Robert Williams | Stephen Yao Agbeli | Operations | 3 | SIB Bank Liberia | - | RESOLVED | Client advised to use the lien screen to unblock it. | 2022-05-09 14:32 | As stated in the log
2 | 2022-05-06 11:24 | IN00006448 | NRA -PLATFORM | I hereby write to report that teller Salamtu Okyne with ID 001462 tried to post into NRA platform an amount of Le 4,661,100 PRN NUMBER 000000000 TIN 1000106489 . The amount hit the customer ITAS account at NRA but not the teller float account 003006037582113155 and the customer is now requesting for a printout of the payment. | MARIAMA KALLON | ********COMMENT 1 ***** Reply From Hamza Alieu : Resolved [Date Posted] :2022-05-06 19:44:19 | Hamza Alieu Sesay | Mohamed L Jalloh | Nii Ayi Welbeck | Cash Operation / Teller | 3 | SIERRA LEONE COMMERCIAL BANK | - | RESOLVED | Receipt expected details was manually inputted in order to reprint the receipt for the customer and advise given for transaction to be manually posted. | 2022-05-06 20:05 | NRA transactions was posted using the NRA portal and didn reflected on the tellers float account but reflected to NRA
3 | 2022-05-05 04:45 | IN00006446 | RCA REQUIRED TEST | This is a test incident to ensure all fields in the rca are required and duly filled before it goes through successfully. | Joshua Amarfio | ********COMMENT 1 ***** Reply From Joshua : its yours now... [Date Posted] :2022-05-05 04:45:42 | Joshua Armarfio | Joshua Armarfio | USG | Browser | 3 | USG | - | RESOLVED |  | 2022-05-11 03:57 | adhkfh
1 | 2022-04-29 08:32 | IN00006435 | ERROR DURNING POSTING INTO NRA PORTAL | An error occur during posting into NRA portal, the tellers float account was not credited making it impossible for the teller to debit the customers account. Account no 079308, account name Education Centre for the blind. Kindly help investigate and solve the issue. | Phebian C. Koroma | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-29 08:34:54 ********COMMENT 2 ***** Reply From Hamza Alieu : Kindly provide us the error message [Date Posted] :2022-04-29 12:11:31 ********COMMENT 3 ***** Reply From Hamza Alieu : Advise given [Date Posted] :2022-04-29 18:02:13 ********COMMENT 4 ***** Reply From TAMBA : Confirmed [Date Posted] :2022-04-29 18:44:15 | Hamza Alieu Sesay | TAMBA MOHAMED SANDY | Nii Ayi Welbeck | Operations | 3 | SIERRA LEONE COMMERCIAL BANK | - | CLOSED | an advise given to debit the customers and credit the tellers float account using the back office single payment screen for the teller to balance | 2022-04-29 18:14 | Transaction posted reflected to NRA but didn debited the customer and also failed to credit the tellers float account.
2 | 2022-04-28 13:30 | IN00006431 | UNABLE TO VIEW DOCUMENT (S) IN X100+ | The following documents with reference number; 1645425336, 1645425309, 1645425284, 1645425448 and 1645425474 cannot be opened and the information that popped up reads "A Valid Document ID is required". Kindly do the needful to address this issue as i am under immense pressure to submit this work today. | Ahmed Conteh | ********COMMENT 1 ***** Reply From Helpdesk : Nii, kindly help. [Date Posted] :2022-04-28 14:16:16 ********COMMENT 2 ***** Reply From TAMBA : Hello team, any update on this issue. The customer is running out of patience. Since yesterday he has not been able to do his work because of this document viewing issues. [Date Posted] :2022-04-29 11:45:15 ********COMMENT 3 ***** Reply From Hamza Alieu : Done [Date Posted] :2022-04-29 17:17:14 ********COMMENT 4 ***** Reply From TAMBA : Resolved [Date Posted] :2022-04-29 18:01:36 | Hamza Alieu Sesay | TAMBA MOHAMED SANDY | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | - | CLOSED | Documents re-scanned | 2022-04-29 17:38 | Document server was crashed
3 | 2022-04-26 11:16 | IN00006424 | REQUEST FOR INFORMATION | Kindly provide the rest of the data from inception to 2018 with the same format. Please treat as urgent. @Hamza, Please see request from Tito same data as previuosly requested ,please take note of the preriod inception to 2018. | Ibrahim G. Sankoh | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-26 11:21:04 ********COMMENT 2 ***** Reply From Nii Ayi : Hamza for your attention [Date Posted] :2022-04-26 17:05:05 ********COMMENT 3 ***** Reply From Hamza Alieu : Working in progress [Date Posted] :2022-04-26 19:39:02 ********COMMENT 4 ***** Reply From TAMBA : Resolved [Date Posted] :2022-04-29 11:20:49 | Hamza Alieu Sesay | TAMBA MOHAMED SANDY | Nii Ayi Welbeck | Operations | 3 | SIERRA LEONE COMMERCIAL BANK | - | CLOSED | Script write to get the requested report | 2022-04-28 13:05 | Request for audit purpose
4 | 2022-04-25 16:39 | IN00006421 | INTERACTIVE LOG ON BY BANKOWNER DISABLED | As agreed with Jude of USG that after the creation of all DB users, BANKOWNER will be disabled to interactively log on into the DB. Please let us know when to come and check to ensure that it has been implemented. | Albert Macfoy | ********COMMENT 1 ***** Reply From Helpdesk : Hello Nii Ayi, kindly help. [Date Posted] :2022-04-25 16:41:21 ********COMMENT 2 ***** Reply From TAMBA : Confirmed [Date Posted] :2022-04-26 10:35:27 | Nii Ayi Welbeck | TAMBA MOHAMED SANDY | Nii Ayi Welbeck | Others | 3 | SIERRA LEONE COMMERCIAL BANK | - | CLOSED | implemented as agreed. | 2022-04-25 17:09 | Explanation is given