## slcb_upgrade_by_departments
Task ID	Task Description	Project Name	Start Date	End Date	Department	Rate	Owner
REF000055	Ability to restore staff after termination	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF000056	Ability to capture system transfer dates on system and actual staff transfer dates	SLCB HR	2022-02-07	2022-02-15	Enterprise Solutions	40%	Henry Caleb Amoh
REF000057	Replace logged in employee id with employee id	SLCB HR	2022-02-07	2022-02-15	Enterprise Solutions	70%	Paul George Yidana
REF000058	Ability to capture actual date for suspension and termination	SLCB HR	2022-02-07	2022-02-15	Enterprise Solutions	100%	Paul George Yidana
REF000085	Remove social security and ethnicity from employee data	SLCB HR	2022-02-07	2022-02-15	Enterprise Solutions	100%	Paul George Yidana
REF000086	Add residential and email address for emergency contacts	SLCB HR	2022-02-07	2022-02-15	Enterprise Solutions	100%	Paul George Yidana
REF000087	Ability to filter staff records by employee number, paygrade, staff level and age	SLCB HR	2022-02-07	2022-02-28	Enterprise Solutions	100%	Paul George Yidana
REF000088	create staff retirement screen to show staff who are a year to retirement	SLCB HR	2022-02-07	2022-02-28	Enterprise Solutions	30%	Paul George Yidana
REF000089	Ability to filter staff records by recruitment date	SLCB HR	2022-02-07	2022-02-28	Enterprise Solutions	100%	Paul George Yidana
REF000091	Each staff level should be apportioned amounts representing basic	SLCB HR	2022-02-07	2022-02-28	Enterprise Solutions	0%	Paul George Yidana
REF000093	Create screen for paygrade/staff level so that an increment in an allowance will affect all staff for a particular notch	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF000095	Make provision for capturing number of working days	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF000096	Create emolument report that contains staff allowances for an entire year based on the current amount	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF000097	Leave subsidy/allowance should be active when number of leave days is above 10 working days	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000153	Add ICT department to leave approval levels	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000156	Unpaid Leaves should be well handled to prevent staff from receiving allowances	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000157	Add to leave approval notification whether a staff will be paid leave allowance or not	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000158	Compassionate leave amount should be applied to leaves taken for compasionate leaves	SLCB HR	2022-02-07	2022-04-29	Enterprise Solutions	0%	Paul George Yidana
REF0000161	Design a summary report on all branches/depts/unit leaves (sample report to be received from Edna/Theresa)	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000163	Employee expense report not responding	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000165	Apply calculation columns to notches	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000176	Make provision for expense beneficiary dept/unit/branch	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000177	Make provision for internal medicals. Medical unit should be able to capture medical records for record keeping and analytics at employee module	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	70%	Paul George Yidana
REF0000178	create screen for reducing balance on medicals	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	80%	Paul George Yidana
REF0000180	Make provision for training cost payments through swift	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000183	Managers should be able to request for staff training. It goes through line manager/supervision, to HR, DMD/MD and then back to HR	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	80%	Paul George Yidana
REF0000214	Add links to e-learning (eg Coursera) platforms on course/training sessions	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000215	Disciplinary records should be added to employee profile to indicate summary termination/dismissals	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000217	Disciplinary actions should include seization, advice to resign, surcharge, warnings, reprimand, forfeiture etc	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000218	Create summary report on self assesment and appraisal	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000219	Take performance review template to be fed into the system	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	30%	Paul George Yidana
REF0000221	Add option to download report in excel/pdf	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000222	Create Disciplinary report	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000223	Replace asset code with serial number	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000224	Enable private chats	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Henry Caleb Amoh
REF0000225	Loan origination process should be added to the system	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	0%	Paul George Yidana
REF0000226	Ability to send HR forms on the system with email notification. And to receive email notification when they are received/returned	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	80%	Henry Caleb Amoh
REF0000227	PAYE sample report to be taken from Theresa for appropriate adjustments	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	100%	Paul George Yidana
REF0000720	VREG CROSS - Reports on Total Loans, O/D, Contingent and NPA Statement of loans and Advances(CBWSR002)Total O/D figure on this cluster does not equal to Total O/D on the balance sheet and Other advances(Contingent) was not provided for on this cluster	SLCB UPGRADE	2022-02-15	2022-07-15	Enterprise Solutions	0%	Joseph Boateng
REF0000721	VREG CROSS - Reports on sectoral classification weekly Statement of Sectoral Adverse Classification(CBWSR009)Incomplete framework (i.e. No Security Reliable, No Provision made, No Interest in Suspense)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000722	VREG CROSS - Reports on Total Loans, O/D and NPA Statement of Risk Assets by Major Economic Sector(CBMSR1004)The breakdown is not seen (CBMSR1004)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000723	VREG CROSS - Reports on sectoral classification Monthly Statement of Sectoral Adverse Classification(CBMSR015)Incomplete framework (i.e. No Security Realizable, No Provision made, No Interest in Suspense)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000724	VREG CROSS - Reports on Commercial & Personal Lending Statement of Commercial and Personal Lending(CBMSR020)Not Seen(Error Message- REP-110: File CBMSR020.rdf cannot open)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000725	VREG CROSS - Outstanding loan to Major Economic Activity Breakdown of Loans Outstanding by M.E.A(CBMSB1021)Not seen (CBMSB1021)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000726	VREG CROSS - Analysis of O/D, Loans, Advances Breakdown of Statement of Analysis of O/D, Loans, Advances(CBMS1022)Not seen (CBMS1022)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000727	VREG CROSS - Analysis of O/D, Loans, Advances Statement of Analysis of O/D, Loans and Adv. Of Banking Insti. (CBMSR025)This cluster needs further Sub Segment(Public Institutions, Joint State and Private, Co-operative Etc.)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000728	VREG CROSS - Top Borrows Statement of Top 50 Borrows (CBMSR052) Some fields are still empty (i.e. Â Collateral, Collateral Reference, Collateral Value) Report do not update.	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000729	VREG CROSS - Sectoral Classification Breakdown of Sectoral Classification(CBMSB1053)The breakdown is not seen (CBMSB1053)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000730	VREG CROSS - Adverse Classification Statement of List of Adverse Classification (CBMRS054)Some fields are still empty( i.e. Â Collateral type, Value of Collateral, Drawn down Amt, Maturity date, Approve Amt, Interest ) Report do not Update.	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000731	VREG CROSS - Quarterly Info of Specific loss and Actual loss and Provisions STATEMENT OF SPECIFIC LOSS PROVISIONS AND ACTUAL LOSS (CBQSR001)Framework Ok yet to verify the correctness of the figures.	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000732	VREG CROSS - Restructured Credit Outstanding STATEMENT OF RESTRUCTURED CREDITS OUTSTANDING (CBQSR003)Framework Ok yet to verify the correctness of the figures	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000733	VREG CROSS - STATEMENT OF RECLASSIFICATIONS TO PERFORMING STATUS AND WRITE-OFFS (CBQSR004)Framework Ok yet to verify the correctness of the figures	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000734	VREG CROSS - STATEMENT OF CREDITS TO DIRECTORS, OFFICERS, EMPLOYEES AND ETC (CBQSR005)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000735	VREG CROSS - BREAKDOWN OF VALUE OF LOAN ACCOUNTS BY MAJOR ECONOMIC ACTIVITIES(CBQSB1006)Not seen (CBQSB1006)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000736	VREG CROSS - STATEMENT OF NON-CURRENT AND NON-ACCRUAL CREDIT OUTSTANDING(CBQSR013)Not Seen (CBQSR013)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000737	VREG CROSS - BREAKDOWN OF CREDITS TO AFFILIATED COMPANIES(CBQSR015)Incomplete Framework (i.e. Other Column Not Seen)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000738	VREG CROSS - O/D,Loans, and other Facilities extended to Employees STATEMENT OF OVERDRAFT, LOANS AND OTHER CREDIT FACILITIES EXTENDED TO OFFICIAL AND OTHER EMPLOYEES OF THE BANK(CBHYSR007)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000741	VREG CROSS - Immovable Property for Shareholders and Directors STATEMENT OF IMMOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR SHAREHOLDERS AND DIRECTORS(CBHYSR008)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000742	VREG CROSS - Movable Property for Shareholders and Directors STATEMENT OF MOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR SHAREHOLDERS AND DIRECTORS(CBHYSR009)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000744	VREG CROSS - Immovable Property for Other Officials and Employees STATEMENT OF IMMOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR OTHER OFFICALS AND EMPLOYEES(CBHYSR010)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000745	VREG CROSS - Movable Property for Other Officials and Employees STATEMENT OF MOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR OTHER OFFICALS AND EMPLOYEES(CBHYSR011)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000748	VREG CROSS - Immovable Property for Other STATEMENT OF IMMOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR OTHERS (CBHYSR012)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000750	VREG CROSS - Movable Property for Other STATEMENT OF MOVABLE PROPERTY ACCEPTED IN SATISFACTION OF DEBT FOR OTHERS (CBHYSR013)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000751	VREG CROSS - STATEMENT OF ADVANCES CREDIT AND GUARANTEES GRANTED TO DIRECTORS AS % OF CAPITAL BASE(CBHYSR014)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000752	VREG CROSS - Account Witten Off STATEMENT OF LIST OF ACCOUNT WRITTEN OFF IN THE LAST TWO YEARS(CBHYSR015)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000753	VREG CROSS - NET EXPOSURE REPORT The following total in this report is incorrect: Total loans and Advances, Contingent, Performing and Nonâ€‘Performing loans and O/D.	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000754	VREG CROSS - ALL CLUSTERS SHOULD HAVE REFRESH DATE (i.e. START DATE AND END DATE)	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000755	VREG CROSS - Onsite Pre-Exam Ciuster Statement OF REPOSSESSED/SEIZED ASSETS (CBPESR002)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000756	VREG CROSS - Onsite Pre-Exam Ciuster STATEMENT OF DIRECTORS AND OFFICERS INDEBTEDNESS(CBPESR006)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000757	VREG CROSS - Onsite Pre-Exam Ciuster STATEMENT OF INSIDER RELATED CREDITS(CBPESR007)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000758	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Insider Related Credits - Ex Staff(CBPECR008)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000759	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Outstanding Facilities to Government and Its Agencies(CBPESR014)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000760	VREG CROSS - Onsite Pre-Exam Ciuster Statement of List of Accounts Written Off In the Last Two Years(CBPESR018)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000761	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Schedule of Provision Required(CBPESR022)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000762	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Detailed Customer Credit Information(CBPESR024)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000763	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Loans and Advances to Directors and Officers of Other Banks(CBPESR026)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000764	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Loans and Advances to Accounts Lawyers, Consultants and Other Professionals(CBPESR027)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000765	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Letter Of Credit (Loans and Advances to Accounts Lawyers, Consultants and Other Professionals)(CBPESR028)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000766	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Acceptances(CBPESR029)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000767	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Loans and Advances Secured By Customer's Own Deposits(CBPESR030)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000768	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Government Guaranteed Loans(CBPESR031)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000769	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Loans Secured By Shares of Stock in Other Non-Bank Financial Institutions(CBPESR032)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000770	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Securities File/Register(CBPESR036)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000771	VREG CROSS - Onsite Pre-Exam Ciuster Statement of List of Loans not Accruing Interest(CBPESR037)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000772	VREG CROSS - Onsite Pre-Exam Ciuster Statement of Past Due Loan(CBPESR039)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000773	VREG CROSS - CIS Statement of Collateral Information(CBAWCR009)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	0%	Joseph Boateng
REF0000774	VREG CROSS - CISEnd Of Credit Transaction(CBMCR001)Not Seen	SLCB UPGRADE	2022-02-15	2022-07-14	Enterprise Solutions	10%	Joseph Boateng
REF00001115	FIXED ASSET RETIREMENT	FIXED ASSET	2022-04-22	2022-04-23	Enterprise Solutions	80%	Prince Manu
REF00001319	PC CODE tagging staff	PC CODE CREATION	2022-05-17	2022-05-20	Enterprise Solutions	100%	Gaddiel Essuman-Acquah
REF00001354	Add download button for downloading of medical attachment	SLCB HR	2022-05-23	2022-05-23	Enterprise Solutions	100%	Henry Caleb Amoh