## vw_tasks_by_departments
Task Id	Task Description	Client	Completion Rate	Status	Start Date	End Date	Owner	Priority
REF0000706	System Functionality - Advances: Provisioning etc. not working to satisfaction (Auto Provisioning by system based on BSL guidelines)	SIERRA LEONE COMMERCIAL BANK	0%	in progress	2022-02-15	2022-07-15	Joseph Boateng	high
REF0000707	System Functionality - ADVANCES: Approval Workflow to be completed	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000708	System Functionality - Collections Queue: Items dealt with still remain in queue	SIERRA LEONE COMMERCIAL BANK	0%	in progress	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000709	System Functionality - Collections: SMS & email messages not being sent to clients	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000710	System Functionality - REJECTION OF BCA REQUEST: Ability to redirect to appropriate party in approval process	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000711	System Functionality - BCA Approval process: Replace IDs with Names or Add Names to the IDs displayed	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000712	System Functionality - BCA Queue : Clearly separate all the category of : DECLINE; REFERRAL; APPROVED	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high
REF0000713	System Functionality - Expired overdrafts duplicate information on accounts	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-15	2022-07-14	Joseph Boateng	high