## vw_tasks_by_departments
Task Id	Task Description	Client	Completion Rate	Status	Start Date	End Date	Owner	Priority
REF0000851	System Functionality - Creating New users requires security staff to copy and send password via email. System should automatically send new user password after email address is entered.	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-17	2022-07-17	Isaac Wilson	high
REF0000852	System Functionality - New user password created does not have user ID included in the new password prompt. However No.6 (previous issue)addresses this.	SIERRA LEONE COMMERCIAL BANK	0%	not started	2022-02-17	2022-07-16	Isaac Wilson	high
REF0000853	System Functionality - Categorize Users List (System Setup â€“> General Administration â€“> No.1. Users List) by branch/dept	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-17	2022-07-16	Isaac Wilson	high
REF0000854	System Functionality - Viewing of own account transactions is restricted	SIERRA LEONE COMMERCIAL BANK	100%	completed	2022-02-17	2022-07-16	Isaac Wilson	high
REF0000855	System Functionality - Exporting reports to Excel still an issue	SIERRA LEONE COMMERCIAL BANK	0%	not started	2022-02-17	2022-07-16	Isaac Wilson	high
REF0000856	System Functionality - When a form module is added to a user's profile, the Audit Trail does not show the form module added	SIERRA LEONE COMMERCIAL BANK	0%	not started	2022-02-17	2022-07-16	Isaac Wilson	high
REF0000857	System Functionality - Ability to Grant specific (standalone ) access rather than Group as is now	SIERRA LEONE COMMERCIAL BANK	0%	not started	2022-02-17	2022-07-16	Isaac Wilson	high