## vw_tasks_by_departments
Task ID	Task Description	Project Name	Start Date	End Date	Department	Rate	Owner
REF000045	Authentication	SLCB Mobile App	2022-02-08	2022-02-11	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000066	Login	SLCB Mobile App	2022-02-08	2022-02-09	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000067	Enroll on app	SLCB Mobile App	2022-02-09	2022-02-10	Mobile Solutions	80%	Gilbert Laud Akakpo
REF000069	First Time Login Setup	SLCB Mobile App	2022-02-10	2022-02-11	Mobile Solutions	80%	Gilbert Laud Akakpo
REF000070	Forgot Password	SLCB Mobile App	2022-02-09	2022-02-10	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000079	Forgot Pin	SLCB Mobile App	2022-02-11	2022-02-14	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000080	Change Password	SLCB Mobile App	2022-02-14	2022-02-16	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000081	Braches locator	SLCB Mobile App	2022-02-17	2022-02-18	Mobile Solutions	80%	Gilbert Laud Akakpo
REF000082	Help	SLCB Mobile App	2022-02-16	2022-02-17	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000083	About Us	SLCB Mobile App	2022-02-18	2022-02-18	Mobile Solutions	100%	Gilbert Laud Akakpo
REF000084	Home page design ( last login, accounts, features, mini statement)	SLCB Mobile App	2022-02-09	2022-02-10	Mobile Solutions	100%	Elijah Ashitey
REF000098	Own Account Transfer	SLCB Mobile App	2022-02-11	2022-02-14	Mobile Solutions	100%	Elijah Ashitey
REF000099	Same Bank Transfer	SLCB Mobile App	2022-02-14	2022-02-15	Mobile Solutions	100%	Elijah Ashitey
REF0000100	Other Bank Transfer	SLCB Mobile App	2022-02-15	2022-02-16	Mobile Solutions	100%	Elijah Ashitey
REF0000101	International Transfer	SLCB Mobile App	2022-02-17	2022-02-18	Mobile Solutions	0%	Elijah Ashitey
REF0000103	Africel Topup	SLCB Mobile App	2022-02-22	2022-02-23	Mobile Solutions	100%	Elijah Ashitey
REF0000127	Account to Momo	SLCB Mobile App	2022-02-23	2022-02-24	Mobile Solutions	100%	Elijah Ashitey
REF0000128	Momo to Account	SLCB Mobile App	2022-02-24	2022-02-25	Mobile Solutions	100%	Elijah Ashitey
REF0000130	Blink Pay	SLCB Mobile App	2022-02-25	2022-02-28	Mobile Solutions	100%	Elijah Ashitey
REF0000132	QR Payment	SLCB Mobile App	2022-03-01	2022-03-02	Mobile Solutions	0%	Elijah Ashitey
REF0000134	EDSA Payment	SLCB Mobile App	2022-03-02	2022-03-03	Mobile Solutions	100%	Elijah Ashitey
REF0000137	School Payment	SLCB Mobile App	2022-03-04	2022-03-07	Mobile Solutions	0%	Elijah Ashitey
REF0000138	Biometric Setup	SLCB Mobile App	2022-02-21	2022-02-22	Mobile Solutions	100%	Elijah Ashitey
REF0000139	Biometric Setup	SLCB Mobile App	2022-02-18	2022-02-21	Mobile Solutions	100%	Gilbert Laud Akakpo
REF0000148	Fast Balance Activation	SLCB Mobile App	2022-02-24	2022-02-22	Mobile Solutions	100%	Gilbert Laud Akakpo
REF0000175	Account Opening	SLCB Mobile App	2022-02-24	2022-02-28	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000184	Additional account creation	SLCB Mobile App	2022-02-28	2022-03-01	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000186	Beneficiary (add, manage, delete and view )	SLCB Mobile App	2022-03-01	2022-03-04	Mobile Solutions	80%	Gilbert Laud Akakpo
REF0000192	Cheque Book Request	SLCB Mobile App	2022-03-07	2022-03-08	Mobile Solutions	80%	Gilbert Laud Akakpo
REF0000194	Salary Advance	SLCB Mobile App	2022-03-07	2022-03-08	Mobile Solutions	70%	Elijah Ashitey
REF0000196	Statement Request	SLCB Mobile App	2022-03-08	2022-03-09	Mobile Solutions	70%	Gilbert Laud Akakpo
REF0000202	Stop Cheque	SLCB Mobile App	2022-03-09	2022-03-10	Mobile Solutions	70%	Gilbert Laud Akakpo
REF0000204	FX Rates	SLCB Mobile App	2022-03-09	2022-03-10	Mobile Solutions	100%	Gilbert Laud Akakpo
REF0000207	Customer Complaint	SLCB Mobile App	2022-03-11	2022-03-16	Mobile Solutions	100%	Gilbert Laud Akakpo
REF0000208	Loans	SLCB Mobile App	2022-03-10	2022-03-23	Mobile Solutions	0%	Elijah Ashitey
REF0000210	Investment	SLCB Mobile App	2022-03-14	2022-03-18	Mobile Solutions	20%	Gilbert Laud Akakpo
REF0000313	BulkTransfer	Corporate Internet Banking	2022-02-09	2022-02-18	Mobile Solutions	100%	Joshua Tetteh
REF0000331	Login	POS	2022-02-15	2022-02-16	Mobile Solutions	0%	Elijah Ashitey
REF0000332	Home Page	POS	2022-02-16	2022-02-17	Mobile Solutions	0%	Elijah Ashitey
REF0000333	Balance Enquiry	POS	2022-02-17	2022-02-18	Mobile Solutions	0%	Elijah Ashitey
REF0000334	Cash Services	POS	2022-02-18	2022-02-21	Mobile Solutions	0%	Elijah Ashitey
REF0000335	Card Services	POS	2022-02-21	2022-02-22	Mobile Solutions	0%	Elijah Ashitey
REF0000336	Cheque Services	POS	2022-02-22	2022-02-23	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000337	Standing Instruction	POS	2022-02-23	2022-02-25	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000338	Remittance	POS	2022-02-23	2022-02-24	Mobile Solutions	0%	Elijah Ashitey
REF0000339	Account Opening	POS	2022-02-22	2022-02-25	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000340	Bills Payment	POS	2022-02-25	2022-02-28	Mobile Solutions	0%	Elijah Ashitey
REF0000347	Account Services	POS	2022-02-25	2022-03-02	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000350	Teller Statistics	POS	2022-02-28	2022-03-02	Mobile Solutions	0%	Elijah Ashitey
REF0000352	Cheque Deposit	POS	2022-03-02	2022-03-04	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000354	Cheque Withdrawals	POS	2022-03-03	2022-03-07	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000355	Cash Deposit	POS	2022-03-02	2022-03-04	Mobile Solutions	0%	Elijah Ashitey
REF0000356	Cash Withdrawal	POS	2022-03-03	2022-03-07	Mobile Solutions	0%	Elijah Ashitey
REF0000357	Cash Funds Transfer	POS	2022-03-04	2022-03-10	Mobile Solutions	0%	Elijah Ashitey
REF0000363	Card Services(card request, card block and replacement, pin re-issuance)	POS	2022-03-10	2022-03-23	Mobile Solutions	0%	Gilbert Laud Akakpo
REF0000368	Bills Payment(Momo, Airtime, Utilities,Education, Government)	POS	2022-03-10	2022-03-23	Mobile Solutions	0%	Elijah Ashitey
REF0000369	Remittance( Send and Receive Money)	POS	2022-03-23	2022-03-29	Mobile Solutions	0%	Elijah Ashitey
REF0000420	Orange transfer procedure amendments	SLCB Orange transfer procedure amendments	2022-02-14	2022-03-31	Mobile Solutions	0%	Jude Kuwornu
REF00001004	Generate swift confirmation file	Swift Confirmation File SLCB (MT103)	2022-03-07	2022-03-18	Mobile Solutions	100%	Daniel Hammond Jr.
REF00001005	Send confirmation file to trustlink directory	Swift Confirmation File SLCB (MT103)	2022-03-07	2022-03-18	Mobile Solutions	100%	Daniel Hammond Jr.
REF00001060	Change PIN	SLCB Mobile App	2022-03-28	2022-03-31	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001061	Fast Balance Deactivation	SLCB Mobile App	2022-03-16	2022-03-30	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001062	View Fast Balance	SLCB Mobile App	2022-03-14	2022-03-22	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001080	Orange Redenomination Test Environment	Redenomination Test Environment Set up	2022-04-04	2022-04-08	Mobile Solutions	100%	Daniel Hammond Jr.
REF00001082	Africel Redenomination Test Environment	Redenomination Test Environment Set up	2022-04-18	2022-04-22	Mobile Solutions	100%	Daniel Hammond Jr.
REF00001107	Salone Link	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001108	Get Charge on Remittance Amount	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001109	Africel Top up	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	100%	Jonathan Markin
REF00001110	Account to Momo	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	100%	Jonathan Markin
REF00001111	Momo To Account	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	100%	Jonathan Markin
REF00001112	Blink Pay	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001129	New User Document for SLCB Mobile App Upgrade	User Document for Digital Products	2022-04-22	2022-05-01	Mobile Solutions	0%	Victoria Delali Ake
REF00001146	Edsa Payment	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	100%	Jonathan Markin
REF00001147	Edsa Reprint	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001150	USL Fees Payment	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001151	Narration Edit	SLCB APIs - Mobile App Upgrade	2022-04-01	2022-05-31	Mobile Solutions	0%	Jonathan Markin
REF00001188	Transaction History	SLCB Mobile App	2022-03-20	2022-04-27	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001193	Share Account Information	SLCB Mobile App	2022-04-22	2022-04-25	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001194	Switch Accounts for History	SLCB Mobile App	2022-04-25	2022-04-26	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001195	Filter Transaction History	SLCB Mobile App	2022-04-25	2022-04-26	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001197	App theme conformity on various screens	SLCB Mobile App	2022-04-26	2022-05-02	Mobile Solutions	90%	Gilbert Laud Akakpo
REF00001204	My Accounts Display	SLCB Mobile App	2022-04-26	2022-05-05	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001206	Validate User Endpoint	SLCB APIs - Mobile App Upgrade	2022-04-25	2022-04-26	Mobile Solutions	100%	Jonathan Markin
REF00001210	Set Default QR Account	SLCB Mobile App	2022-04-26	2022-05-02	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001219	Ts & Cs	SLCB Mobile App	2022-04-28	2022-05-05	Mobile Solutions	90%	Gilbert Laud Akakpo
REF00001224	Default QR Code	SLCB Mobile App	1970-01-01	1970-01-01	Mobile Solutions	100%	Gilbert Laud Akakpo
REF00001249	Salone Link	SLCB Mobile App	2022-05-04	2022-05-10	Mobile Solutions	80%	Gilbert Laud Akakpo
REF00001279	Bank Genie Test Environment Set Up	Redenomination Test Environment Set up	2022-05-02	2022-05-13	Mobile Solutions	100%	Daniel Hammond Jr.
REF00001345	Dangote UAT Frontend	Integrator Payments Tracking and Optimization	2022-05-19	2022-05-25	Mobile Solutions	50%	Joshua Tetteh
REF00001346	Dangote UAT Backend	Integrator Payments Tracking and Optimization	2022-05-19	2022-05-25	Mobile Solutions	0%	Jonathan Markin
REF00001347	NRA Transactions JSON Log	Integrator Payments Tracking and Optimization	2022-05-20	2022-05-23	Mobile Solutions	0%	Jonathan Markin
REF00001380	Editing transfer confirmation details	SLCB Mobile App	2022-05-25	2022-05-25	Mobile Solutions	100%	Elijah Ashitey
REF00001381	OTP confirmation forms	SLCB Mobile App	2022-05-25	2022-05-25	Mobile Solutions	30%	Elijah Ashitey
REF00001389	Add extra check in procedures to ensure that transactions are actually in AC_TRANS before sending response	ENHANCING SECURITY	2022-05-30	2022-06-03	Mobile Solutions	0%	Daniel Hammond Jr.
REF00001390	Add extra check in procedures to ensure that transactions are actually in AC_TRANS before sending response	ENHANCING SECURITY	2022-05-30	2022-06-03	Mobile Solutions	0%	Daniel Hammond Jr.
REF00001391	Add extra check in procedures to ensure that transactions are actually in AC_TRANS before sending response	ENHANCING SECURITY	2022-05-30	2022-06-03	Mobile Solutions	0%	Daniel Hammond Jr.
REF00001393	Combined Utility Payments	SLCB Mobile App	2022-05-17	2022-05-25	Mobile Solutions	90%	Gilbert Laud Akakpo
REF00001394	Combined Airtime Topup	SLCB Mobile App	2022-05-20	2022-05-22	Mobile Solutions	90%	Gilbert Laud Akakpo