## vw_last_update_orginal
Project ID	Project Description	Start Date	End Date	Department	Completion	Client	Owner	Status	Last Update	Last Update Date
PROJ-000010	Imprest Request	01/25/22	02/11/22	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Prince Manu	completed	the enquiry shows all the imprest request (pending approval,approved ,rejected,and ones that have been withdrawn	2022-02-11 11:19:18
PROJ-000027	MIS DATA MINING MODULE	01/25/22	02/25/22	Enterprise Solutions	87.1429%	UNION SYSTEMS GLOBAL	Samuel Adjetey Anang	in progress	Page Design and Creation in Progress.	2022-02-11 11:40:19
PROJ-0000103	Report template orientation amendment	02/14/22	02/14/22	Credits	100.0000%	Rokel Commercial Bank	Kofi Agbexwe Annan	completed	Report was restructured according to the template presented. Report tested and implemented.	2022-02-18 12:34:21
PROJ-000039	USL FEES PAYMENT	02/09/22	03/11/22	Mobile Solutions	95.0000%	Union Trust Bank	Joshua Tetteh	in progress	Waiting for project to be signed of by RM	2022-02-18 14:02:22
PROJ-0000121	USSD for SUSU Accounts sends wrong SMS	02/15/22	02/18/22	Mobile Solutions	80.0000%	BEST POINT	Daniel Hammond Jr.	in progress	Awaiting @Daniel Koranteng 's confirmation	2022-02-21 08:37:25
PROJ-0000135	Create Enquiry Screen for TODs	02/18/22	02/18/22	Credits	90.0000%	Rokel Commercial Bank	Kofi Agbexwe Annan	in progress	Project completed. Pending review and testing.	2022-02-23 15:18:05
PROJ-00001	Project Tracker User Manual Doc	02/02/22	02/28/22	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Joshua Amarfio	completed	From page 11 to page 15 gives guidelines on how to give updates on a project using the message or the comment feature...	2022-02-24 12:30:49
PROJ-000026	Hr changes for UTB	02/08/22	02/28/22	Enterprise Solutions	100.0000%	Union Trust Bank	Henry Caleb Amoh	completed	Payroll report screen also completed	2022-02-25 15:22:55
PROJ-00009	TB_VALIDATION	02/09/22	03/08/22	MIS/Special Projects	60.0000%	UNION SYSTEMS GLOBAL	Prince Manu	in progress	table is been created to help identify all invalid transactions that failed. the following are inserted into the table ACCT_LINK, BATCH_NO, VOUCHER_NUMBER, TRANS_TYPE, USERNAME, AMOUNT	2022-02-28 10:10:58
PROJ-000024	SLCB PROCUREMENT REQUESTS	01/04/22	02/28/22	Enterprise Solutions	63.1034%	UNION SYSTEMS GLOBAL	Bernice Boadi	in progress	Users are able to track to the negotiation stage	2022-02-28 17:36:01
PROJ-000067	X.100 Big Manual	02/01/22	12/31/22	Service Management	31.5789%	UNION SYSTEMS GLOBAL	Naa Ashianor	in progress	worked on it	2022-03-01 16:35:06
PROJ-000057	ORACLE LINUX AND WINDOWS MONITORING TOOL	02/09/22	02/18/22	Systems	20.0000%	UNION SYSTEMS GLOBAL	Caleb Armarfio	in progress	A shell script have done to give notifications on usage of oracle root space.	2022-03-02 09:25:06
PROJ-0000146	UTB NRA EOD AND DAILY STATEMENT	12/30/21	03/04/22	Mobile Solutions	100.0000%	Union Trust Bank	Daniel Hammond Jr.	completed	task completed...	2022-03-06 08:49:50
PROJ-0000123	ROKEL ESTATEMENT	02/15/22	02/25/22	Mobile Solutions	100.0000%	Rokel Commercial Bank	Daniel Hammond Jr.	completed	Encryptions completed and mails are being sent successfully	2022-03-06 09:10:24
PROJ-00006	HR CHANGES FOR RCB (SL)	02/07/22	04/29/22	Enterprise Solutions	42.2222%	Rokel Commercial Bank	Paul George Yidana	in progress	Reconciliation/correction completed. This happened as a result of table and column mismatch.	2022-03-14 08:08:36
PROJ-0000153	Other Assignments	03/01/22	12/31/22	Service Management	100.0000%	Rokel Commercial Bank	Naa Ashianor	completed	the lady came and we had the walk through. she was pleased with what she saw	2022-03-18 12:35:00
PROJ-000089	Create a test server	02/10/22	02/11/22	Systems	100.0000%	UNION SYSTEMS GLOBAL	Moses O. Atakorah	completed	Drive mapped	2022-03-21 09:22:35
PROJ-000016	SLCB HR	02/07/22	03/31/22	Enterprise Solutions	49.2105%	SIERRA LEONE COMMERCIAL BANK	Paul George Yidana	in progress	A generic PAYE Report has been created to cater for all PAYE reports needed	2022-03-21 11:08:58
PROJ-000034	Personal Internet Banking	10/08/21	04/30/22	Mobile Solutions	36.3636%	Rokel Commercial Bank	Dennis Gyamfi	in progress	Currency conversion when making international transfers	2022-03-28 17:40:28
PROJ-0000174	RO creation	04/05/22	04/15/22	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Henry Caleb Amoh	completed	The task given to me on this project are currently completed and pending new tasks if any	2022-04-09 13:00:42
PROJ-0000170	working on X-100 React-UI	04/04/22	11/10/22	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Godfrey Twene	completed	all icons are added and changed to png file format	2022-04-12 17:44:54
PROJ-0000173	Test, implementation of new eod g_ledger balance updates	04/07/22	04/21/22	Enterprise Solutions	40.0000%	UNION SYSTEMS GLOBAL	Stanley Okyere-Agyei	in progress	1.Completed on the rcb environment, awaiting input from isaac and bandoh. 2.Awaiting to implement on the slcb envrionment upon setup completion. 3.Upon approval, the processes will be rolled out	2022-04-14 19:10:54
PROJ-0000145	Issue logger	02/24/22	12/31/22	Enterprise Solutions	42.0000%	UNION SYSTEMS GLOBAL	Joshua Amarfio	in progress	attached to this message is the table for departments...	2022-04-15 18:21:17