## vw_last_update_orginal
Project ID	Project Name	Start Date	End Date	Department	completion	Client	Owner	Status	Last Update	Last Update Date
PROJ-000010	Imprest Request	2022-02-09	2022-02-09	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Prince Manu	completed	the enquiry shows all the imprest request (pending approval,approved ,rejected,and ones that have been withdrawn	2022-02-11 11:19:18
PROJ-000027	MIS DATA MINING MODULE	2022-01-25	2022-01-28	Enterprise Solutions	87.1429%	UNION SYSTEMS GLOBAL	Samuel Adjetey Anang	in progress	Page Design and Creation in Progress.	2022-02-11 11:40:19
PROJ-0000103	Report template orientation amendment	2022-02-14	2022-02-14	Credits	100.0000%	Rokel Commercial Bank	Kofi Agbexwe Annan	completed	Report was restructured according to the template presented. Report tested and implemented.	2022-02-18 12:34:21
PROJ-000039	USL FEES PAYMENT	2022-02-09	2022-02-11	Channels	95.0000%	Union Trust Bank	Joshua Tetteh	in progress	Waiting for project to be signed of by RM	2022-02-18 14:02:22
PROJ-0000121	USSD for SUSU Accounts sends wrong SMS	2022-02-15	2022-02-18	Channels	80.0000%	BEST POINT	Daniel Hammond Jr.	in progress	Awaiting @Daniel Koranteng 's confirmation	2022-02-21 08:37:25
PROJ-0000135	Create Enquiry Screen for TODs	2022-02-18	2022-02-18	Credits	90.0000%	Rokel Commercial Bank	Kofi Agbexwe Annan	in progress	Project completed. Pending review and testing.	2022-02-23 15:18:05
PROJ-00001	Project Tracker User Manual Doc	2022-02-02	2022-02-03	Enterprise Solutions	100.0000%	UNION SYSTEMS GLOBAL	Joshua Amarfio	completed	From page 11 to page 15 gives guidelines on how to give updates on a project using the message or the comment feature...	2022-02-24 12:30:49
PROJ-000026	Hr changes for UTB	2022-02-08	2022-02-09	Enterprise Solutions	100.0000%	Union Trust Bank	Henry Caleb Amoh	completed	Payroll report screen also completed	2022-02-25 15:22:55
PROJ-00009	TB_VALIDATION	2022-02-09	2022-02-15	MIS/Special Projects	60.0000%	UNION SYSTEMS GLOBAL	Prince Manu	in progress	table is been created to help identify all invalid transactions that failed. the following are inserted into the table ACCT_LINK, BATCH_NO, VOUCHER_NUMBER, TRANS_TYPE, USERNAME, AMOUNT	2022-02-28 10:10:58
PROJ-000024	SLCB PROCUREMENT REQUESTS	2022-02-07	2022-02-28	Enterprise Solutions	61.7241%	UNION SYSTEMS GLOBAL	Bernice Boadi	in progress	Users are able to track to the negotiation stage	2022-02-28 17:36:01
PROJ-000067	X.100 Big Manual	2022-04-01	2022-05-31	Service Management	31.5789%	UNION SYSTEMS GLOBAL	Naa Ashianor	in progress	worked on it	2022-03-01 16:35:06
PROJ-000057	ORACLE LINUX AND WINDOWS MONITORING TOOL	2022-02-09	2022-02-18	Systems	20.0000%	UNION SYSTEMS GLOBAL	Caleb Armarfio	in progress	A shell script have done to give notifications on usage of oracle root space.	2022-03-02 09:25:06
PROJ-0000146	UTB NRA EOD AND DAILY STATEMENT	2021-12-30	2022-03-03	Channels	100.0000%	Union Trust Bank	Daniel Hammond Jr.	completed	task completed...	2022-03-06 08:49:50
PROJ-0000123	ROKEL ESTATEMENT	2022-02-15	2022-02-25	Channels	100.0000%	Rokel Commercial Bank	Daniel Hammond Jr.	completed	Encryptions completed and mails are being sent successfully	2022-03-06 09:10:24
PROJ-00006	HR CHANGES FOR RCB (SL)	2022-02-07	2022-03-30	Enterprise Solutions	42.2222%	Rokel Commercial Bank	Paul George Yidana	in progress	Reconciliation/correction completed. This happened as a result of table and column mismatch.	2022-03-14 08:08:36
PROJ-0000153	Other Assignments	2022-03-03	2022-03-03	Service Management	100.0000%	Rokel Commercial Bank	Naa Ashianor	completed	the lady came and we had the walk through. she was pleased with what she saw	2022-03-18 12:35:00
PROJ-000089	Create a test server	2022-02-10	2022-02-11	Systems	100.0000%	UNION SYSTEMS GLOBAL	Moses O. Atakorah	completed	Drive mapped	2022-03-21 09:22:35
PROJ-000016	SLCB HR	2022-02-07	2022-03-31	Enterprise Solutions	45.5263%	SIERRA LEONE COMMERCIAL BANK	Paul George Yidana	in progress	A generic PAYE Report has been created to cater for all PAYE reports needed	2022-03-21 11:08:58
PROJ-000034	Personal Internet Banking	2022-02-07	2022-02-11	Channels	36.3636%	Rokel Commercial Bank	Dennis Gyamfi	in progress	Currency conversion when making international transfers	2022-03-28 17:40:28
PROJ-0000145	Issue logger	2022-04-11	2022-04-15	Enterprise Solutions	36.6667%	UNION SYSTEMS GLOBAL	Joshua Amarfio	in progress	database fields added accordingly and uis as well. yet to finalize on the issue.	2022-03-29 16:36:36
PROJ-0000157	ENHANCING SECURITY	2022-03-22	2022-07-31	Channels	10.0000%	UNION SYSTEMS GLOBAL	Daniel Hammond Jr.	in progress	updates on all channel procedures to not accept GLs	2022-04-05 09:07:44
PROJ-00002	Project Tracker Application	2022-02-09	2022-02-28	Enterprise Solutions	75.3333%	UNION SYSTEMS GLOBAL	Joshua Amarfio	in progress	sample has been done and downloaded and is pending review.	2022-04-08 17:15:47
PROJ-0000174	RO creation	2022-04-05	2022-04-15	Enterprise Solutions	0.0000%	UNION SYSTEMS GLOBAL	Henry Caleb Amoh	in progress	The task given to me on this project are currently completed and pending new tasks if any	2022-04-09 13:00:42