## API UPGRADE CONSOLIDATION
SLCB API CONSOLIDATION, REVIEW & DOCUMENTATION - PROJECT PLAN
Task Name | Duration | Work | Expected Start Date | Expected Completion Date | % Completion | Status | Comments
Union Systems Global | 56 days | 1299 hrs | 2024-02-07 | 2024-04-25 | 80% | Pending
Technical Set-up & Preparation | 1 day | 3 hrs | 2024-02-07 | 2024-02-07
Get Access to API Servers | within a day | 5 hrs | 2024-02-07 | 2024-02-07 | 100% | DONE
Test and ensure everything is working | within a day | 3 hrs | 2024-02-07 | 2024-02-07 | 100% | DONE
ORANGE BW API | 2 days | 48 hrs | 2024-02-08 | 2024-02-09
Review request and response parameters. Evaluate ORANGE API. | within a day | 6 hrs | 2024-02-08 | 2024-02-08 | 100% | DONE
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-02-08 | 2024-02-08 | 100% | DONE
Document Orange BW Integration | 1 day | 8 hrs | 2024-02-09 | 2024-02-09 | 100% | DONE
AFRIMONEY BW API | 2 days | 48 hrs | 2024-02-12 | 2024-02-13
Review request and response parameters. Review AFRIMONEY API. | within a day | 6 hrs | 2024-02-12 | 2024-02-12 | 100% | DONE
Validate input / output, test for robustness. | within a day | 2 hrs | 2024-02-12 | 2024-02-13 | 100% | DONE
Document Afrimoney BW Integration | 1 day | 8 hrs | 2024-02-13 | 2024-02-13 | 100% | DONE
EDSA BW API | 2 days | 48 hrs | 2024-02-14 | 2024-02-15
Review request and response parameters. Review EDSA API code. | within a day | 6 hrs | 2024-02-14 | 2024-02-14 | 100% | DONE
Check documentation, error handling, standards. | within a day | 2 hrs | 2024-02-14 | 2024-02-14 | 100% | DONE
Document EDSA BW Integration | 1 day | 8 hrs | 2024-02-15 | 2024-02-15 | 100% | DONE
DANGOTE BW API | 2 days | 48 hrs | 2024-02-16 | 2024-02-19
Review request and response parameters. Evaluate DANGOTE API. | within a day | 6 hrs | 2024-02-16 | 2024-02-16 | 100% | DONE
Ensure data accuracy, security, error handling. | within a day | 2 hrs | 2024-02-16 | 2024-02-16 | 100% | DONE
Document DANGOTE BW Integration | 1 day | 8 hrs | 2024-02-19 | 2024-02-19 | 100% | DONE
NRA / ITAS API | 2 days | 48 hrs | 2024-02-20 | 2024-02-21
Review request and response parameters. Examine NRA API. | within a day | 6 hrs | 2024-02-20 | 2024-02-20 | 100% | DONE
Confirm compliance, scalability, and performance. | within a day | 2 hrs | 2024-02-20 | 2024-02-20 | 100% | DONE
Document NRA / ITAS Integration | 1 day | 8 hrs | 2024-02-21 | 2024-02-21 | 100% | DONE
PAPSS BW API | 2 days | 48 hrs | 2024-02-22 | 2024-02-23
Review request and response parameters. Assess PAPSS API. | within a day | 6 hrs | 2024-02-22 | 2024-02-22 | 100% | DONE
Verify data validation, logging, and system integration. | within a day | 2 hrs | 2024-02-22 | 2024-02-22 | 100% | DONE
Document PAPSS BW Integration | 1 day | 8 hrs | 2024-02-23 | 2024-02-23 | 100% | DONE
SMALLWORLD BW API | 2 days | 48 hrs | 2024-02-26 | 2024-02-27
Review request and response parameters. Inspect SMALLWORLD API. | within a day | 6 hrs | 2024-02-26 | 2024-02-26 | 100% | DONE
Examine data integrity, response time, and optimizations. | within a day | 2 hrs | 2024-02-26 | 2024-02-26 | 100% | DONE
Provide Documenation for SMALLWORLD | 1 day | 8 hrs | 2024-02-27 | 2024-02-27 | 100% | DONE
BANK GENI (MIYONNE TELLER) API | 2 days | 48 hrs | 2024-02-28 | 2024-02-29
Review request and response parameters. Evaluate Bank Geni API. | within a day | 6 hrs | 2024-02-28 | 2024-02-28 | 100% | DONE | Windows Config: We currently do not have the source codes. Re-engineering done pending testing.
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-02-28 | 2024-02-28 | 100% | DONE | Windows Config: We currently do not have the source codes. Re-engineering done pending testing.
Provide Documenation for Bank Geni with X100 | 1 day | 8 hrs | 2024-02-29 | 2024-02-29 | 100% | DONE | Windows Config: We currently do not have the source codes. Re-engineering done pending testing.
MERCURY API | 2 days | 48 hrs | 2024-03-01 | 2024-03-04
Review request and response parameters. Evaluate MERCURY API. | within a day | 6 hrs | 2024-03-01 | 2024-03-01 | 100% | DONE
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-03-01 | 2024-03-01 | 100% | DONE
Document Mercury BW Integration | 1 day | 8 hrs | 2024-03-04 | 2024-03-04 | 100% | DONE
SLRSA API REVIEW | 2 days | 48 hrs | 2024-03-05 | 2024-03-06
Review request and response parameters. Evaluate SLRSA API. | within a day | 6 hrs | 2024-03-05 | 2024-03-05 | 100% | DONE
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-03-05 | 2024-03-05 | 100% | DONE
Document SLRSA BW Integration | 1 day | 8 hrs | 2024-03-06 | 2024-03-06 | 100% | DONE
WALLET REVIEW | 2 days | 48 hrs | 2024-03-07 | 2024-03-08
Review request and response parameters. Evaluate Wallet API. | within a day | 6 hrs | 2024-03-07 | 2024-03-07 | 100% | DONE | WIndows Config: A new Wallet API has been developed.
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-03-07 | 2024-03-07 | 100% | DONE | WIndows Config: A new Wallet API has been developed.
Provide Documenation for Wallet Integration with X100 | 1 day | 8 hrs | 2024-03-08 | 2024-03-08 | 100% | DONE | WIndows Config: A new Wallet API has been developed.
SecurityPort REVIEW | 2 days | 48 hrs | 2024-03-11 | 2024-03-12
Review request and response parameters. Evaluate SecurityPort API. | within a day | 6 hrs | 2024-03-11 | 2024-03-11 | 100% | DONE
Check authentication, encryption, and security measures. | within a day | 2 hrs | 2024-03-11 | 2024-03-11 | 100% | DONE
Document SecurityPort BW Integration | 1 day | 8 hrs | 2024-03-12 | 2024-03-12 | 100% | DONE
NRA ECR INTEGRATION | 2 day | 24 hrs | 2024-03-13 | 2024-03-14
Implement the NRA ECR Integration | 1 day | 8 hrs | 2024-03-13 | 2024-03-13 | 100% | DONE | New project, currently in development queue
Document NRA ECR Integration | 1 day | 8 hrs | 2024-03-14 | 2024-03-14 | 100% | DONE | New project, currently in development queue
CARD FUSION | 2 day | 48 hrs | 2024-03-15 | 2024-03-18
Implement the Card Fusion API's for Interswitch. (i.e. Name Enquiry, Account Payment, Notification) | 1 day | 24 hrs | 2024-03-15 | 2024-03-15 | 100% | DONE
Document Card Fusion Integration | 1 day | 24 hrs | 2024-03-18 | 2024-03-18 | 100% | DONE
RESOLVE EXISTING API ISSUES | 1 day | 24 hrs | 2024-03-19 | 2024-03-20
Disable API Updating TB Relations | 1 day | 8 hrs | 2024-03-19 | 2024-03-19 | 100% | DONE | False alarm: We have not found any such API
Disable API Updating Branch Name | 1 day | 8 hrs | 2024-03-20 | 2024-03-20 | 100% | DONE | False alarm: We have not found any such API
CONSOLIDATION OF APIs UNTO THE LINUX TEST ENVIRONMENT | 5 days | 120 hrs | 2024-03-21 | 2024-03-27
Core API v1.0 | Within a day | 2.7 hrs | 2024-03-21 | 2024-03-21 | 100% | DONE
Integrator API (i.e USL, EDSA, Dycar, SecurePort, TransFlow, NRA, NCRA,Mercury, Africel) | Within a day | 2.7 hrs | 2024-03-21 | 2024-03-21 | 100% | DONE
E-mail , SMS , E-statement , Inter-switch ATM Gateways, Generate SWIFT MT103 FILES | Within a day | 2.7 hrs | 2024-03-21 | 2024-03-21 | 100% | DONE
Dangote API | Within a day | 2.7 hrs | 2024-03-22 | 2024-03-22 | 100% | DONE
Ibanking and CIB API | Within a day | 2.7 hrs | 2024-03-22 | 2024-03-22 | 100% | DONE
New CIB Core API | Within a day | 2.7 hrs | 2024-03-22 | 2024-03-22 | 100% | DONE
InterSwitch - Card Fusion | Within a day | 2.7 hrs | 2024-03-22 | 2024-03-22 | 100% | DONE
New Core API v1.0 | 1 day | 8 hrs | 2024-03-25 | 2024-03-25 | 100% | DONE | A new version of the Core API v1.0. This takes into consideration all the vulnerabilities in old Core v1.0 API
Wallet | 1 day | 8 hrs | 2024-03-26 | 2024-03-26 | 100% | DONE | Windows Config. We do not have the source codes, thus, we have developed a new one.
PAPPS | Within a day | 2.7 hrs | 2024-03-27 | 2024-03-27 | 100% | DONE
Orange | Within a day | 2.7 hrs | 2024-03-27 | 2024-03-27 | 100% | DONE
Old ATM Gateway | Within a day | 2.7 hrs | 2024-03-27 | 2024-03-27 | 100% | DONE | Windows Config. We currently do not have the source codes. Slated for Re-engineering. Re-engineering.
Miyonne Teller & Bank Genie API | Within a day | 2.7 hrs | 2024-03-27 | 2024-03-27 | 100% | DONE | Windows Config: We currently do not have the source codes. Re-engineering done pending testing.
NRA ECR INTEGRATION | Within a day | 2.7 hrs | 2024-03-27 | 2024-03-27 | 100% | DONE | New Project
Database Credentials Powered by Block-chain API | 5 days | 120 hrs | 2024-03-28 | 2024-04-03
Core API v1.0 | Within a day | 2.7 hrs | 2024-03-28 | 2024-03-28 | 100% | DONE
Integrator API (i.e USL, EDSA, Dycar, SecurePort, TransFlow, NRA, NCRA, Mercury, Africel) | Within a day | 2.7 hrs | 2024-03-28 | 2024-03-28 | 100% | DONE
E-mail Gateway, SMS Gateway, E-statement Gateway | Within a day | 2.7 hrs | 2024-03-28 | 2024-03-28 | 100% | DONE
Ibanking and CIB API | Within a day | 2.7 hrs | 2024-03-29 | 2024-03-29 | 100% | DONE
Wallet | Within a day | 2.7 hrs | 2024-03-29 | 2024-03-29 | 100% | DONE
Miyonne Teller API (Bank Genie) | Within a day | 2.7 hrs | 2024-03-29 | 2024-03-29 | 100% | DONE
Inter-switch ATM | Within a day | 2.7 hrs | 2024-04-01 | 2024-04-01 | 100% | DONE
Instant Payment - Card Fusion | Within a day | 2.7 hrs | 2024-04-01 | 2024-04-01 | 100% | DONE
Old ATM Gateway | Within a day | 2.7 hrs | 2024-04-01 | 2024-04-01 | 100% | DONE
Dangote API | Within a day | 2.7 hrs | 2024-04-02 | 2024-04-02 | 100% | DONE
New Core API v1.0 | Within a day | 2.7 hrs | 2024-04-02 | 2024-04-02 | 100% | DONE
New CIB Core API | Within a day | 2.7 hrs | 2024-04-02 | 2024-04-02 | 100% | DONE
NRA ECR INTEGRATION | Within a day | 4hrs | 2024-04-03 | 2024-04-03 | 100% | DONE
PAPPS | Within a day | 2hrs | 2024-04-03 | 2024-04-03 | 100% | DONE
Generate SWIFT MT103 FILES | Within a day | 2hrs | 2024-04-03 | 2024-04-03 | 100 % | DONE
ACTUAL END-TO-END TESTING OF CONSOLIDATED APIS ON LINUX ENV. | 10 days | 240 hrs | 2024-04-04 | 2024-04-04
Instant Payment - Card Fusion | 1 day | 4 hrs | 2024-04-04 | 2024-04-04 | 100% | DONE
Name Enquiry | Within a day | 1 hr | 2024-04-04 | 2024-04-04 | 100% | DONE
Account Payment | Within a day | 1 hr | 2024-04-04 | 2024-04-04 | 100% | DONE
Notification | Within a day | 1 hr | 2024-04-04 | 2024-04-04 | 100% | DONE
NEW CIB | 1 day | 4 hrs | 2024-04-05 | 2024-04-05 | 100% | DONE
Account Information | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Account Statement | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Account Balance | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Funds Transfer | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Transaction Reversal | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Transaction Status | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Customer Accounts By Account Number | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Customer Accounts By Customer ID | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Customer Details By Phone Number | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Customer Details By Account Number | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Call Deposit By Account Number | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Call Deposit By Customer ID | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Loan Summary | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Loan Schedule | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Monthly Turnover | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Stop Cheque | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Cheque Book Request | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Card Statement | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Money Market Investment | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Charge Details | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
Get Relation Officer Details By Customer Number | Within a day | 11 mins | 2024-04-05 | 2024-04-05 | 100% | DONE
PAYMENTS | 1 day | 8 hrs | 2024-04-08 | 2024-04-08 | 100% | Pending
NRA | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE
USL | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE
EDSA | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE
TRANSFLOW | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Not in use
MERCURY | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Not in use
NCRA | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Not in use
DANGOTE | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Pending frontend dev.
SECUREPORT | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Not in use
PAPSS | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE
SLSRA | Within a day | 48 mins | 2024-04-08 | 2024-04-08 | 100% | DONE | Not in use
MOBILE APP | 1 day | 8 hrs | 2024-04-09 | 2024-04-09
Airtime Topup(Africel) | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Account to Mobile Money(Africel) | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 0% | Pending | Africel needs to whitelist the ip of the linux test env.
Mobile Money to Account(Africel) | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 0% | Pending | Africel needs to whitelist the ip of the linux test env.
Blink Pay | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
QR Payment | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Utility Payment (Dycar, National ID) | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Airport Tax | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
School Payments | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Instant Payment | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 0% | Pending | In development
Statement Request | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Request Cheque Book | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Stop Cheque | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Salary Advance | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Add Account | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
View Forex Rate | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Card Request | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Own Account Transfer | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Same Bank Transfer | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Other Bank Transfer | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Transfer Tracking(ACH) | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Salone Link | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
Standing Order | Within a day | 21 mins | 2024-04-09 | 2024-04-09 | 100% | DONE
PERSONAL INTERNET BANKING | 1 day | 8 hrs | 2024-04-10 | 2024-04-10
Account Enquiry | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Own Account Transfer | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Same Bank Transfer | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Other Bank Transfer (RTGS) | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Other Bank Transfer (ACH) | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Standing Order | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Standing Order Status | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Transfer Beneficiaries | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Payment(Mobile Money Transfer - Africell) | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Airport Tax | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
National ID | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Salone Link | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
QR Payment | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Payment Beneficiaries | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Loans Enquiry | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Salary Advance | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Cheque Book Request | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Stop Cheque | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Statement Request | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Make Complaint | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Card Request | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Block Card | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Activate Card | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Change Transaction Pin | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Change Password | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
Forget Transaction Pin | Within a day | 17 mins | 2024-04-10 | 2024-04-10 | 100% | DONE
CORPORATE INTERNET BANKING | 1 day | 8 hrs | 2024-04-11 | 2024-04-11
Account Enquiry | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Own Account Transfer | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Same Bank Transfer | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Other Bank Transfer (RTGS) | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Other Bank Transfer (ACH) | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
International Transfer | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Standing Order | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Transfer Beneficiaries | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Same Bank Bulk Transfer | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Payment(Mobile Money Transfer - Africell) | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Airport Tax | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
National ID | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
QR Payment | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Salone Link | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Payment Beneficiaries | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Loans Enquiry | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Stop Cheque | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Cheque Book Request | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Statement Request | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Approvals( Pending, Approved, Rejected) | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Make Complaint | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Settings( Create Originator, Change Password, Create Authorizer) | Within a day | 21 mins | 2024-04-11 | 2024-04-11 | 0% | Pending | Currently connecting to live db directly. Slated for re-engineering; to call an api.
Gateways | 1 day | 8 hrs | 2024-04-12 | 2024-04-12
Old ATM Gateway | Within a day | 36 mins | 2024-04-12 | 2024-04-12 | 0% | Pending
E-mail Gateway | Within a day | 36 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
SMS Gateway | Within a day | 36 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
E-statement Gateway | Within a day | 36 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Inter-switch ATM Gateway | Within a day | 15 mins | 2024-04-12 | 2024-04-12 | 0% | Pending
Generate SWIFT MT103 FILES | Within a day | 15 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Wallet | 1 day | 8 hrs | 2024-04-12 | 2024-04-12
Get user details | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Get customer details | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Get user transactions | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Perform Transfer | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Bank to wallet transfer | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Wallet to bank transfer | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Transaction reversal | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Register momo user | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Get info | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Get account details | Within a day | 48 mins | 2024-04-12 | 2024-04-12 | 100% | DONE
Miyonne Teller | 1 day | 8 hrs | 2024-04-15 | 2024-04-15
Withdrawal | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Treasury Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Statement Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
SMS | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
SLink Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
SLink Redeem Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
SLink Funds Transfer Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Reversal Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
New Account Creation Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
New Account Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Lov Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Mini Statement Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Balance Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Funds Transfer Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Fees Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Deposit Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Customer Phone Number Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Get Customer Info Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Cheque Withdrawal Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Cheque Validity Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Cheque Book Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
Cheque Fund Transfer Request | Within a day | 21 mins | 2024-04-15 | 2024-04-15 | 0% | Pending
New Core API v1.0 | 1 day | 8 hrs | 2024-04-16 | 2024-04-16
User Password Change | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
User Login | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
User Treasury Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Retrieve User Balance | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
User Transaction | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
System Status | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Withdrawal Reversal | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
ATM Service Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Cancel Standing Order | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Standing Order Enquiry | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Stop Cheque Service Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Standing Order Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
SMS Service Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Email Service Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Verify Cheque Number | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Statement Service Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Cheque Book Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD User Details | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD User Registration | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD Pin Validation | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD Pin Change | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD Registration With ID | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD Check Registration | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
USSD User (If User Is Registered) | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
ATM Card Applicants | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Exchange Rates | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Forex Rates | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Loan Quotation | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
LOv Codes | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Smart Branch Lov Codes | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Customer Create Account | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Customer Complaint | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Customer Fixed Deposit | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Customer Login | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Customer Info | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Create Account | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Clearing Cheque Deposit | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Deposit Dangote Cheque | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Cheque Deposit | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Cheque Withdrawal | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Create Account New | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Create Fixed Deposit | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Create Rtgs Payment | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Transaction Status | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Get Transaction With RefNo | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Transfer funds With Fees | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Account Deposit With Currency | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Retrieve Account Mandate | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
User Transaction | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Validate Cheque | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Withdraw Money | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Investment Balances | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Cheque Deposit ACH | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Account Linkage Status | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Bulk Credit | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Bulk Payment | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Transaction Status | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Mini Statement Request | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Balance Enquiry | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Reverse Transaction | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Transfer (Same Bank) | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Other Bank Transfer Status | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Transfer(Other Banks) | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Retrieve Account By Customer Number | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Retrieve Account By Phone Number | Within a day | 8mins | 2024-04-16 | 2024-04-16 | 100% | DONE
Orange API | 1 day | 154 mins | 2024-04-17 | 2024-04-17
Account Information | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Account Balance | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Wallet to Bank Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Bank to Wallet Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Funds Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Transactions Status | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Account Linkage Status | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Africel API | 1 day | 154 mins | 2024-04-17 | 2024-04-17
Account Information | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Account Balance | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Wallet to Bank Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Bank to Wallet Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Funds Transfer | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Transaction Status | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
Account Linkage Status | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 100% | DONE
NRA ECR INTEGRATION | 1 day | 154 mins | 2024-04-17 | 2024-04-17
Send Invoice Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Send Refund Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Send Payment Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Send Discount Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Send Item Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Send Receipt Data | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
Comment Text | Within a day | 22 mins | 2024-04-17 | 2024-04-17 | 0% | Pending
CONSOLIDATION AND TESTING OF APIs ON THE vxRAIL (PRODUCTION ENV.) | 5 days | 120 hrs | 2024-04-18 | 2024-04-24
Core API | Day 1 (Within a day) | 2.7 hrs | 2024-04-18 | 2024-04-18 | 50% | In Progress | Consolidation has been done, pending testing.
Integrator API (i.e USL, EDSA, Dycar, SecurePort, TransFlow, NRA, NCRA,Mercury, Africel) | Day 1 (Within a day) | 2.7 hrs | 2024-04-18 | 2024-04-18 | 50% | In Progress | Consolidation has been done, pending testing.
E-mail , SMS , E-statement , Inter-switch ATM Gateways | Day 1 (Within a day) | 2.7 hrs | 2024-04-18 | 2024-04-18 | 50% | In Progress | Consolidation has been done, pending testing.
Dangote API | Day 2 (Within a day) | 2.7 hrs | 2024-04-19 | 2024-04-19 | 50% | In Progress | Consolidation has been done, pending testing.
Ibanking and CIB API | Day 2 (Within a day) | 2.7 hrs | 2024-04-19 | 2024-04-19 | 50% | In Progress | Consolidation has been done, pending testing.
New CIB Core API | Day 2 (Within a day) | 2.7 hrs | 2024-04-19 | 2024-04-19 | 50% | In Progress | Consolidation has been done, pending testing.
InterSwitch - Card Fusion | Day 3 (Within a day) | 2.7 hrs | 2024-04-22 | 2024-04-22 | 50% | In Progress | Consolidation has been done, pending testing.
New Core API v1.0 | Day 3 (Within a day) | 2.7 hrs | 2024-04-22 | 2024-04-22 | 50% | In Progress | Consolidation has been done, pending testing.
Wallet | Day 3 (Within a day) | 2.7 hrs | 2024-04-22 | 2024-04-22 | 50% | In Progress | Consolidation has been done, pending testing.
PAPPS | Day 4 (Within a day) | 4 hrs | 2024-04-23 | 2024-04-23 | 50% | In Progress | Consolidation has been done, pending testing.
Orange | Day 4 (Within a day) | 4 hrs | 2024-04-23 | 2024-04-23 | 50% | In Progress | Consolidation has been done, pending testing.
Old ATM Gateway | Day 5 (Within a day) | 2.7 hrs | 2024-04-24 | 2024-04-24 | 50% | In Progress | Consolidation has been done, pending testing.
Miyonne Teller & Bank Genie API | Day 5 (Within a day) | 2.7 hrs | 2024-04-24 | 2024-04-24 | 50% | In Progress | Consolidation has been done, pending testing.
NRA ECR INTEGRATION | Day 5 (Within a day) | 2.7 hrs | 2024-04-24 | 2024-04-24 | 50% | In Progress | Consolidation has been done, pending testing.
CLOSURE STAGE | 1 day | 24 hrs | 2024-04-25 | 2024-04-25
Ensure All Reviewed API's are Working Fine | within a day | 6 hrs | 2024-04-25 | 2024-04-25 | 0% | Pending
Project Closure | within a day | 2 hrs | 2024-04-25 | 2024-04-25 | 0% | Pending

## OTHERS
Auxiliary Project - PROJECT PLAN
Task Name | Duration | Work | Expected Start Date | Expected Completion Date | % Completion | Status | Comments
Union Systems Global |  |  |  |  | 0% | Pending
File Transfer - ACP/ACH Swift | 2 days | 48 hrs | 2024-03-22 | 2024-03-25 | 0% | Pending
Reconciliation | 2 days | 48 hrs | 2024-03-26 | 2024-03-27 | 0% | Pending