## Sheet1
Additional Issues After Upgrade
Issue ID | Date Reported | Issue Topic | Description | Category | Severity (H/M/L) | Comment from UTB | Assigned To
1 |  | ATM Card Request File Download | Unable to download ATM card request files from CBA for use on the CMS platform. We will appreciate if this data is extracted from the back-end for swift response so that cards can be processed. Please not to do same for card activation. | CMS | H | USG promised an API that seamlessly connects both systems for card personalization. After the upgrade, this has still not been accomplished | Operations
2 |  | Compulsory SMS and ATM request during account opening. | SMS and ATM cards are requested at account opening, this process is not functional and hence causes the Alert Service to malfunction. Kindly resolve so that it will ease the challenges we have with SMS alerts | Account Opening | H | When this failed process is done, it cause the SMS alert not to function well except they go back and deactivate it and then redo the alert. | Operations | Is working
3 |  | Requesting review of Account Opening Process | The process is extremely lengthy and disjointed. Especially for mandate and signature linkage | Account Opening | H | A total review recommended and should be done alongside UTB and USG. | Operations
4 |  | Manager's Cheque Malfunction | When the manager's cheques are approved, it recreate the request again and put the amount as blocked on the account even though the approval went through. | Operations | M |  | Operations
5 |  | UTB Korpor, sel and redeem | This entire process in not function for both in-branch and digital platform | Digital & CBA | H | This is same for ATM Cardless Redeem and reversal. | Operations | Is working
6 |  | ATM cardless GL malfunction | The ATM Cardless GL is only posting debits and not credits. | Digital & CBA | H | When a transaction is initiated on the Mobile, it should Debit the customer and credit the ATM GL. When the cash is redeemed, it should debit the ATM GL and credit whichever platform the cash was redeemed. | Operations
7 |  | ACH reconcillation | ACH has many outstanding items that needs help from USG to reconcile. | ACH | H | Both teams need to look at the process flow. | Treasury and Payments
8 |  | ATM Card Reissuing | Customer Service are unable to use the ATM card reissuing form to process card replacement | Digital & CBA | H | We have huge amount of cards waiting to be printed | Operations
9 |  | Instant Payment Integration | IP integration with NSSL is still outstanding. We are the only bank that has not started anything. | Digital & CBA | H | We have requested the certificate needed for the IP Server. This has been communicated to Elijah and Daniel Hammond | Channels
10 |  | Foreign Inflows not charging | When we receive inflow, the system fails to charge customers. Kindly fix this. | CBA/Foreign | H |  | Operations
11 |  | USL Payment on digital banking | USL payments need to be added to the Mobile and CIB platforms. T |  |  | This is still outstanding | Channels
12 |  | Account opening rejection | Any account that is opened and sent to supervisor but has issues and rejected to the CS staff, it will lose all the information | Account Opening | M |  | Operations | Might be cancellation not refferral
13 |  | Cheque Book Request on Mobile and CIB | The request does not show on CBA after being initiated on the digital banking platform. | Digital & CBA | M |  | Channels