## Sheet1
New VxRail Implementation Plan
Task | Start Date | End Date | Responsible Party | Notes
Review of applications to be installed | 2023-09-14 | 2023-09-15 | E-Channel, Sys Admin | Completed
Preparation and documentation of the Vxrail | 2023-09-14 | 2023-09-18 | Network, E-Channel, Sys Admin | Completed
Review of the documentation | 2023-09-18 | 2023-09-18 | Network, E-Channel, Sys Admin, ICT Exco | Completed
Communicate agreed documentation to USG | 2023-09-19 | 2023-09-19 | HDTP | Completed
USG get back on the network documentation | 2023-09-29 | 2023-09-29 | USG | Completed
USG get back on the list of servers | 2023-09-29 | 2023-09-29 | USG | Completed
Configuration of the Added VM VLANs on the Dell Switch and Firewalls | 2023-10-23 | 2023-10-24 | USG & SLCB Network | Completed
Addition of the added VLAN networks and VLAN IDs on the VxRail Appliances (HQ & DR Site) | 2023-11-04 | 2023-11-06 | USG Sys Eng & SLCB Sys Admin | Completed
Request for resource allocation for the provision of E-Channel Servers (Resources: CPU, Memory & Storage) | 2023-11-16 | 2023-11-16 | SLCB Sys Admin to USG Team | Completed
USG to get back to us with confirmed list of resource allocation of each e-channel servers to be installed | 2023-11-17 | 2023-11-17 | USG Systems Engineer | Completed
Provision of VMs and Installation of agreed E-Channel Servers on the Vxrail Appliance | 2023-12-16 | 2023-12-18 | USG Systems Engineer & SLCB Sys Admin | Pending
Review of installed e-channel servers and application | 2023-12-16 | 2023-11-18 | E-Channel, Sys Admin, Network & USG | Pending
Patching and hardening of Installed VMs (OS and Software) | 2023-12-17 | 2023-11-18 | USG Systems Engineer and SLCB Sys Admin | Pending
Request for InfoSec Team to scan VxRail Appliance and VMs (servers) for vulnerabilities | 2023-12-17 | 2023-11-18 | SLCB Sys Admin, InfoSec, & Network Teams | Pending
Resolution of any vulnerabilities found from the InfoSec scan result | 2023-12-17 | 2023-12-19 | SLCB Sys Admin, InfoSec, Network Teams & USG Team | Pending
Request for a rescan from InfoSec Team to scan VxRail Appliance and VMs (servers) for vulnerabilities | 2023-12-19 | 2023-12-20 | SLCB Sys Admin, InfoSec, & Network Teams | Pending
Live simulation of replication or vMotion of e-channel servers to DR site from HQ VxRail Appliance | 2023-12-20 | 2023-12-20 | E-Channel, Sys Admin, Network & USG, ICT Exco | Pending
Movement of DR Site VxRail Appliance Servers, Switches and DR Site Fortigate firewall | 2023-12-23 | 2023-12-23 | Sys Admin & Network Teams | Pending
Validation and confirmation of connectivity to DR site for the VxRail Systems from HQ | 2023-12-29 | 2023-12-29 | Network, Sys Admin, ICT Exco & USG | Pending
Final validation and sign off | 19/1/2024 | 19/1/2024 | Network, E-Channel, Sys Admin, ICT Exco | Pending